## Projects_InProgress
ProjectID | ProjectName | Status | DurationDays | Start_Date | End_Date
P005 | Cybersecurity Upgrade | In progress | 283 | 2025-04-10 | 2026-01-18
P001 | Mobile Banking App | In progress | 359 | 2025-04-13 | 2026-04-07
P003 | Data Warehouse Build | In progress | 301 | 2025-04-13 | 2026-02-08
P002 | CRM Upgrade | In progress | 251 | 2025-04-17 | 2025-12-24
P006 | E-commerce Platform | In progress | 232 | 2025-05-30 | 2026-01-17
P016 | Digital Workspace | In progress | 197 | 2025-06-16 | 2025-12-30
P011 | ERP Implementation | In progress | 399 | 2025-06-19 | 2026-07-23

## Resources
ResourceID | Name | Role | MonthlyWageUSD
RES01 | Alice Johnson | Software Developer | 6000
RES02 | Bob Smith | Software Developer | 6200
RES03 | Charlie Brown | Software Developer | 6500
RES04 | Diana Miller | Software Developer | 6800
RES05 | Ethan Davis | Software Developer | 6400
RES06 | Fiona Wilson | Software Developer | 6300
RES07 | Henry Collins | Software Developer | 6600
RES08 | Isabella Wright | Software Developer | 6700
RES09 | Jack Thompson | Software Developer | 6450
RES25 | Wendy Brooks | Software Developer | 6550
RES10 | George Clark | QA / Tester | 5000
RES11 | Hannah Lopez | QA / Tester | 5200
RES12 | Ian Martinez | QA / Tester | 5100
RES13 | Julia Carter | Scrum Master | 7000
RES14 | Kevin Turner | Scrum Master | 7200
RES15 | Laura Adams | Scrum Master | 7100
RES16 | Mark Robinson | Scrum Master | 7300
RES17 | Natalie Perez | Product Owner | 7500
RES18 | Oliver Scott | Product Owner | 7600
RES19 | Paula Edwards | Product Owner | 7400
RES20 | Quentin Hughes | Product Owner | 7700
RES21 | Rachel Foster | UX/UI Designer | 6200
RES22 | Samuel Bennett | DevOps Engineer | 6800
RES23 | Tina Murphy | Architect | 8000
RES24 | Victor Hall | Architect | 8200

## RoleMonthlyDemand
ProjectID | ProjectName | Month | Role | HoursNeeded | FTEsNeeded
P005 | Cybersecurity Upgrade | 2025-04-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2025-04-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2025-04-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-04-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2025-04-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-04-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-04-01 | Architect | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-05-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2025-05-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2025-05-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-05-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2025-05-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-05-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-05-01 | Architect | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-06-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2025-06-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2025-06-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-06-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2025-06-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-06-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-06-01 | Architect | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-07-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2025-07-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2025-07-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-07-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2025-07-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-07-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-07-01 | Architect | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-08-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2025-08-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2025-08-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-08-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2025-08-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-08-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-08-01 | Architect | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-09-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2025-09-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2025-09-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-09-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2025-09-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-09-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-09-01 | Architect | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-10-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2025-10-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2025-10-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-10-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2025-10-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-10-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-10-01 | Architect | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-11-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2025-11-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2025-11-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-11-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2025-11-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-11-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-11-01 | Architect | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-12-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2025-12-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2025-12-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-12-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2025-12-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2025-12-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2025-12-01 | Architect | 40 | 0.25
P005 | Cybersecurity Upgrade | 2026-01-01 | Software Developer | 320 | 2
P005 | Cybersecurity Upgrade | 2026-01-01 | QA / Tester | 160 | 1
P005 | Cybersecurity Upgrade | 2026-01-01 | Scrum Master | 80 | 0.5
P005 | Cybersecurity Upgrade | 2026-01-01 | Product Owner | 160 | 1
P005 | Cybersecurity Upgrade | 2026-01-01 | UX/UI Designer | 80 | 0.5
P005 | Cybersecurity Upgrade | 2026-01-01 | DevOps Engineer | 40 | 0.25
P005 | Cybersecurity Upgrade | 2026-01-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2025-04-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2025-04-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2025-04-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2025-04-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2025-04-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2025-04-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2025-04-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2025-05-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2025-05-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2025-05-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2025-05-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2025-05-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2025-05-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2025-05-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2025-06-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2025-06-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2025-06-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2025-06-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2025-06-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2025-06-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2025-06-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2025-07-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2025-07-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2025-07-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2025-07-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2025-07-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2025-07-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2025-07-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2025-08-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2025-08-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2025-08-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2025-08-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2025-08-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2025-08-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2025-08-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2025-09-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2025-09-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2025-09-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2025-09-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2025-09-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2025-09-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2025-09-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2025-10-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2025-10-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2025-10-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2025-10-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2025-10-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2025-10-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2025-10-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2025-11-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2025-11-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2025-11-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2025-11-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2025-11-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2025-11-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2025-11-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2025-12-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2025-12-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2025-12-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2025-12-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2025-12-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2025-12-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2025-12-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2026-01-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2026-01-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2026-01-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2026-01-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2026-01-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2026-01-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2026-01-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2026-02-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2026-02-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2026-02-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2026-02-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2026-02-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2026-02-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2026-02-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2026-03-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2026-03-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2026-03-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2026-03-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2026-03-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2026-03-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2026-03-01 | Architect | 40 | 0.25
P001 | Mobile Banking App | 2026-04-01 | Software Developer | 320 | 2
P001 | Mobile Banking App | 2026-04-01 | QA / Tester | 160 | 1
P001 | Mobile Banking App | 2026-04-01 | Scrum Master | 80 | 0.5
P001 | Mobile Banking App | 2026-04-01 | Product Owner | 160 | 1
P001 | Mobile Banking App | 2026-04-01 | UX/UI Designer | 80 | 0.5
P001 | Mobile Banking App | 2026-04-01 | DevOps Engineer | 40 | 0.25
P001 | Mobile Banking App | 2026-04-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2025-04-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2025-04-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2025-04-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2025-04-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2025-04-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2025-04-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2025-04-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2025-05-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2025-05-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2025-05-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2025-05-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2025-05-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2025-05-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2025-05-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2025-06-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2025-06-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2025-06-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2025-06-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2025-06-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2025-06-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2025-06-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2025-07-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2025-07-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2025-07-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2025-07-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2025-07-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2025-07-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2025-07-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2025-08-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2025-08-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2025-08-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2025-08-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2025-08-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2025-08-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2025-08-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2025-09-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2025-09-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2025-09-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2025-09-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2025-09-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2025-09-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2025-09-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2025-10-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2025-10-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2025-10-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2025-10-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2025-10-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2025-10-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2025-10-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2025-11-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2025-11-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2025-11-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2025-11-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2025-11-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2025-11-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2025-11-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2025-12-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2025-12-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2025-12-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2025-12-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2025-12-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2025-12-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2025-12-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2026-01-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2026-01-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2026-01-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2026-01-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2026-01-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2026-01-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2026-01-01 | Architect | 40 | 0.25
P003 | Data Warehouse Build | 2026-02-01 | Software Developer | 320 | 2
P003 | Data Warehouse Build | 2026-02-01 | QA / Tester | 160 | 1
P003 | Data Warehouse Build | 2026-02-01 | Scrum Master | 80 | 0.5
P003 | Data Warehouse Build | 2026-02-01 | Product Owner | 160 | 1
P003 | Data Warehouse Build | 2026-02-01 | UX/UI Designer | 80 | 0.5
P003 | Data Warehouse Build | 2026-02-01 | DevOps Engineer | 40 | 0.25
P003 | Data Warehouse Build | 2026-02-01 | Architect | 40 | 0.25
P002 | CRM Upgrade | 2025-04-01 | Software Developer | 320 | 2
P002 | CRM Upgrade | 2025-04-01 | QA / Tester | 160 | 1
P002 | CRM Upgrade | 2025-04-01 | Scrum Master | 80 | 0.5
P002 | CRM Upgrade | 2025-04-01 | Product Owner | 160 | 1
P002 | CRM Upgrade | 2025-04-01 | UX/UI Designer | 80 | 0.5
P002 | CRM Upgrade | 2025-04-01 | DevOps Engineer | 40 | 0.25
P002 | CRM Upgrade | 2025-04-01 | Architect | 40 | 0.25
P002 | CRM Upgrade | 2025-05-01 | Software Developer | 320 | 2
P002 | CRM Upgrade | 2025-05-01 | QA / Tester | 160 | 1
P002 | CRM Upgrade | 2025-05-01 | Scrum Master | 80 | 0.5
P002 | CRM Upgrade | 2025-05-01 | Product Owner | 160 | 1
P002 | CRM Upgrade | 2025-05-01 | UX/UI Designer | 80 | 0.5
P002 | CRM Upgrade | 2025-05-01 | DevOps Engineer | 40 | 0.25
P002 | CRM Upgrade | 2025-05-01 | Architect | 40 | 0.25
P002 | CRM Upgrade | 2025-06-01 | Software Developer | 320 | 2
P002 | CRM Upgrade | 2025-06-01 | QA / Tester | 160 | 1
P002 | CRM Upgrade | 2025-06-01 | Scrum Master | 80 | 0.5
P002 | CRM Upgrade | 2025-06-01 | Product Owner | 160 | 1
P002 | CRM Upgrade | 2025-06-01 | UX/UI Designer | 80 | 0.5
P002 | CRM Upgrade | 2025-06-01 | DevOps Engineer | 40 | 0.25
P002 | CRM Upgrade | 2025-06-01 | Architect | 40 | 0.25
P002 | CRM Upgrade | 2025-07-01 | Software Developer | 320 | 2
P002 | CRM Upgrade | 2025-07-01 | QA / Tester | 160 | 1
P002 | CRM Upgrade | 2025-07-01 | Scrum Master | 80 | 0.5
P002 | CRM Upgrade | 2025-07-01 | Product Owner | 160 | 1
P002 | CRM Upgrade | 2025-07-01 | UX/UI Designer | 80 | 0.5
P002 | CRM Upgrade | 2025-07-01 | DevOps Engineer | 40 | 0.25
P002 | CRM Upgrade | 2025-07-01 | Architect | 40 | 0.25
P002 | CRM Upgrade | 2025-08-01 | Software Developer | 320 | 2
P002 | CRM Upgrade | 2025-08-01 | QA / Tester | 160 | 1
P002 | CRM Upgrade | 2025-08-01 | Scrum Master | 80 | 0.5
P002 | CRM Upgrade | 2025-08-01 | Product Owner | 160 | 1
P002 | CRM Upgrade | 2025-08-01 | UX/UI Designer | 80 | 0.5
P002 | CRM Upgrade | 2025-08-01 | DevOps Engineer | 40 | 0.25
P002 | CRM Upgrade | 2025-08-01 | Architect | 40 | 0.25
P002 | CRM Upgrade | 2025-09-01 | Software Developer | 320 | 2
P002 | CRM Upgrade | 2025-09-01 | QA / Tester | 160 | 1
P002 | CRM Upgrade | 2025-09-01 | Scrum Master | 80 | 0.5
P002 | CRM Upgrade | 2025-09-01 | Product Owner | 160 | 1
P002 | CRM Upgrade | 2025-09-01 | UX/UI Designer | 80 | 0.5
P002 | CRM Upgrade | 2025-09-01 | DevOps Engineer | 40 | 0.25
P002 | CRM Upgrade | 2025-09-01 | Architect | 40 | 0.25
P002 | CRM Upgrade | 2025-10-01 | Software Developer | 320 | 2
P002 | CRM Upgrade | 2025-10-01 | QA / Tester | 160 | 1
P002 | CRM Upgrade | 2025-10-01 | Scrum Master | 80 | 0.5
P002 | CRM Upgrade | 2025-10-01 | Product Owner | 160 | 1
P002 | CRM Upgrade | 2025-10-01 | UX/UI Designer | 80 | 0.5
P002 | CRM Upgrade | 2025-10-01 | DevOps Engineer | 40 | 0.25
P002 | CRM Upgrade | 2025-10-01 | Architect | 40 | 0.25
P002 | CRM Upgrade | 2025-11-01 | Software Developer | 320 | 2
P002 | CRM Upgrade | 2025-11-01 | QA / Tester | 160 | 1
P002 | CRM Upgrade | 2025-11-01 | Scrum Master | 80 | 0.5
P002 | CRM Upgrade | 2025-11-01 | Product Owner | 160 | 1
P002 | CRM Upgrade | 2025-11-01 | UX/UI Designer | 80 | 0.5
P002 | CRM Upgrade | 2025-11-01 | DevOps Engineer | 40 | 0.25
P002 | CRM Upgrade | 2025-11-01 | Architect | 40 | 0.25
P002 | CRM Upgrade | 2025-12-01 | Software Developer | 320 | 2
P002 | CRM Upgrade | 2025-12-01 | QA / Tester | 160 | 1
P002 | CRM Upgrade | 2025-12-01 | Scrum Master | 80 | 0.5
P002 | CRM Upgrade | 2025-12-01 | Product Owner | 160 | 1
P002 | CRM Upgrade | 2025-12-01 | UX/UI Designer | 80 | 0.5
P002 | CRM Upgrade | 2025-12-01 | DevOps Engineer | 40 | 0.25
P002 | CRM Upgrade | 2025-12-01 | Architect | 40 | 0.25
P006 | E-commerce Platform | 2025-05-01 | Software Developer | 320 | 2
P006 | E-commerce Platform | 2025-05-01 | QA / Tester | 160 | 1
P006 | E-commerce Platform | 2025-05-01 | Scrum Master | 80 | 0.5
P006 | E-commerce Platform | 2025-05-01 | Product Owner | 160 | 1
P006 | E-commerce Platform | 2025-05-01 | UX/UI Designer | 80 | 0.5
P006 | E-commerce Platform | 2025-05-01 | DevOps Engineer | 40 | 0.25
P006 | E-commerce Platform | 2025-05-01 | Architect | 40 | 0.25
P006 | E-commerce Platform | 2025-06-01 | Software Developer | 320 | 2
P006 | E-commerce Platform | 2025-06-01 | QA / Tester | 160 | 1
P006 | E-commerce Platform | 2025-06-01 | Scrum Master | 80 | 0.5
P006 | E-commerce Platform | 2025-06-01 | Product Owner | 160 | 1
P006 | E-commerce Platform | 2025-06-01 | UX/UI Designer | 80 | 0.5
P006 | E-commerce Platform | 2025-06-01 | DevOps Engineer | 40 | 0.25
P006 | E-commerce Platform | 2025-06-01 | Architect | 40 | 0.25
P006 | E-commerce Platform | 2025-07-01 | Software Developer | 320 | 2
P006 | E-commerce Platform | 2025-07-01 | QA / Tester | 160 | 1
P006 | E-commerce Platform | 2025-07-01 | Scrum Master | 80 | 0.5
P006 | E-commerce Platform | 2025-07-01 | Product Owner | 160 | 1
P006 | E-commerce Platform | 2025-07-01 | UX/UI Designer | 80 | 0.5
P006 | E-commerce Platform | 2025-07-01 | DevOps Engineer | 40 | 0.25
P006 | E-commerce Platform | 2025-07-01 | Architect | 40 | 0.25
P006 | E-commerce Platform | 2025-08-01 | Software Developer | 320 | 2
P006 | E-commerce Platform | 2025-08-01 | QA / Tester | 160 | 1
P006 | E-commerce Platform | 2025-08-01 | Scrum Master | 80 | 0.5
P006 | E-commerce Platform | 2025-08-01 | Product Owner | 160 | 1
P006 | E-commerce Platform | 2025-08-01 | UX/UI Designer | 80 | 0.5
P006 | E-commerce Platform | 2025-08-01 | DevOps Engineer | 40 | 0.25
P006 | E-commerce Platform | 2025-08-01 | Architect | 40 | 0.25
P006 | E-commerce Platform | 2025-09-01 | Software Developer | 320 | 2
P006 | E-commerce Platform | 2025-09-01 | QA / Tester | 160 | 1
P006 | E-commerce Platform | 2025-09-01 | Scrum Master | 80 | 0.5
P006 | E-commerce Platform | 2025-09-01 | Product Owner | 160 | 1
P006 | E-commerce Platform | 2025-09-01 | UX/UI Designer | 80 | 0.5
P006 | E-commerce Platform | 2025-09-01 | DevOps Engineer | 40 | 0.25
P006 | E-commerce Platform | 2025-09-01 | Architect | 40 | 0.25
P006 | E-commerce Platform | 2025-10-01 | Software Developer | 320 | 2
P006 | E-commerce Platform | 2025-10-01 | QA / Tester | 160 | 1
P006 | E-commerce Platform | 2025-10-01 | Scrum Master | 80 | 0.5
P006 | E-commerce Platform | 2025-10-01 | Product Owner | 160 | 1
P006 | E-commerce Platform | 2025-10-01 | UX/UI Designer | 80 | 0.5
P006 | E-commerce Platform | 2025-10-01 | DevOps Engineer | 40 | 0.25
P006 | E-commerce Platform | 2025-10-01 | Architect | 40 | 0.25
P006 | E-commerce Platform | 2025-11-01 | Software Developer | 320 | 2
P006 | E-commerce Platform | 2025-11-01 | QA / Tester | 160 | 1
P006 | E-commerce Platform | 2025-11-01 | Scrum Master | 80 | 0.5
P006 | E-commerce Platform | 2025-11-01 | Product Owner | 160 | 1
P006 | E-commerce Platform | 2025-11-01 | UX/UI Designer | 80 | 0.5
P006 | E-commerce Platform | 2025-11-01 | DevOps Engineer | 40 | 0.25
P006 | E-commerce Platform | 2025-11-01 | Architect | 40 | 0.25
P006 | E-commerce Platform | 2025-12-01 | Software Developer | 320 | 2
P006 | E-commerce Platform | 2025-12-01 | QA / Tester | 160 | 1
P006 | E-commerce Platform | 2025-12-01 | Scrum Master | 80 | 0.5
P006 | E-commerce Platform | 2025-12-01 | Product Owner | 160 | 1
P006 | E-commerce Platform | 2025-12-01 | UX/UI Designer | 80 | 0.5
P006 | E-commerce Platform | 2025-12-01 | DevOps Engineer | 40 | 0.25
P006 | E-commerce Platform | 2025-12-01 | Architect | 40 | 0.25
P006 | E-commerce Platform | 2026-01-01 | Software Developer | 320 | 2
P006 | E-commerce Platform | 2026-01-01 | QA / Tester | 160 | 1
P006 | E-commerce Platform | 2026-01-01 | Scrum Master | 80 | 0.5
P006 | E-commerce Platform | 2026-01-01 | Product Owner | 160 | 1
P006 | E-commerce Platform | 2026-01-01 | UX/UI Designer | 80 | 0.5
P006 | E-commerce Platform | 2026-01-01 | DevOps Engineer | 40 | 0.25
P006 | E-commerce Platform | 2026-01-01 | Architect | 40 | 0.25
P016 | Digital Workspace | 2025-06-01 | Software Developer | 320 | 2
P016 | Digital Workspace | 2025-06-01 | QA / Tester | 160 | 1
P016 | Digital Workspace | 2025-06-01 | Scrum Master | 80 | 0.5
P016 | Digital Workspace | 2025-06-01 | Product Owner | 160 | 1
P016 | Digital Workspace | 2025-06-01 | UX/UI Designer | 80 | 0.5
P016 | Digital Workspace | 2025-06-01 | DevOps Engineer | 40 | 0.25
P016 | Digital Workspace | 2025-06-01 | Architect | 40 | 0.25
P016 | Digital Workspace | 2025-07-01 | Software Developer | 320 | 2
P016 | Digital Workspace | 2025-07-01 | QA / Tester | 160 | 1
P016 | Digital Workspace | 2025-07-01 | Scrum Master | 80 | 0.5
P016 | Digital Workspace | 2025-07-01 | Product Owner | 160 | 1
P016 | Digital Workspace | 2025-07-01 | UX/UI Designer | 80 | 0.5
P016 | Digital Workspace | 2025-07-01 | DevOps Engineer | 40 | 0.25
P016 | Digital Workspace | 2025-07-01 | Architect | 40 | 0.25
P016 | Digital Workspace | 2025-08-01 | Software Developer | 320 | 2
P016 | Digital Workspace | 2025-08-01 | QA / Tester | 160 | 1
P016 | Digital Workspace | 2025-08-01 | Scrum Master | 80 | 0.5
P016 | Digital Workspace | 2025-08-01 | Product Owner | 160 | 1
P016 | Digital Workspace | 2025-08-01 | UX/UI Designer | 80 | 0.5
P016 | Digital Workspace | 2025-08-01 | DevOps Engineer | 40 | 0.25
P016 | Digital Workspace | 2025-08-01 | Architect | 40 | 0.25
P016 | Digital Workspace | 2025-09-01 | Software Developer | 320 | 2
P016 | Digital Workspace | 2025-09-01 | QA / Tester | 160 | 1
P016 | Digital Workspace | 2025-09-01 | Scrum Master | 80 | 0.5
P016 | Digital Workspace | 2025-09-01 | Product Owner | 160 | 1
P016 | Digital Workspace | 2025-09-01 | UX/UI Designer | 80 | 0.5
P016 | Digital Workspace | 2025-09-01 | DevOps Engineer | 40 | 0.25
P016 | Digital Workspace | 2025-09-01 | Architect | 40 | 0.25
P016 | Digital Workspace | 2025-10-01 | Software Developer | 320 | 2
P016 | Digital Workspace | 2025-10-01 | QA / Tester | 160 | 1
P016 | Digital Workspace | 2025-10-01 | Scrum Master | 80 | 0.5
P016 | Digital Workspace | 2025-10-01 | Product Owner | 160 | 1
P016 | Digital Workspace | 2025-10-01 | UX/UI Designer | 80 | 0.5
P016 | Digital Workspace | 2025-10-01 | DevOps Engineer | 40 | 0.25
P016 | Digital Workspace | 2025-10-01 | Architect | 40 | 0.25
P016 | Digital Workspace | 2025-11-01 | Software Developer | 320 | 2
P016 | Digital Workspace | 2025-11-01 | QA / Tester | 160 | 1
P016 | Digital Workspace | 2025-11-01 | Scrum Master | 80 | 0.5
P016 | Digital Workspace | 2025-11-01 | Product Owner | 160 | 1
P016 | Digital Workspace | 2025-11-01 | UX/UI Designer | 80 | 0.5
P016 | Digital Workspace | 2025-11-01 | DevOps Engineer | 40 | 0.25
P016 | Digital Workspace | 2025-11-01 | Architect | 40 | 0.25
P016 | Digital Workspace | 2025-12-01 | Software Developer | 320 | 2
P016 | Digital Workspace | 2025-12-01 | QA / Tester | 160 | 1
P016 | Digital Workspace | 2025-12-01 | Scrum Master | 80 | 0.5
P016 | Digital Workspace | 2025-12-01 | Product Owner | 160 | 1
P016 | Digital Workspace | 2025-12-01 | UX/UI Designer | 80 | 0.5
P016 | Digital Workspace | 2025-12-01 | DevOps Engineer | 40 | 0.25
P016 | Digital Workspace | 2025-12-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2025-06-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2025-06-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2025-06-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2025-06-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2025-06-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2025-06-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2025-06-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2025-07-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2025-07-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2025-07-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2025-07-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2025-07-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2025-07-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2025-07-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2025-08-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2025-08-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2025-08-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2025-08-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2025-08-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2025-08-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2025-08-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2025-09-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2025-09-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2025-09-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2025-09-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2025-09-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2025-09-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2025-09-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2025-10-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2025-10-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2025-10-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2025-10-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2025-10-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2025-10-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2025-10-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2025-11-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2025-11-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2025-11-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2025-11-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2025-11-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2025-11-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2025-11-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2025-12-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2025-12-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2025-12-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2025-12-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2025-12-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2025-12-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2025-12-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2026-01-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2026-01-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2026-01-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2026-01-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2026-01-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2026-01-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2026-01-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2026-02-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2026-02-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2026-02-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2026-02-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2026-02-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2026-02-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2026-02-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2026-03-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2026-03-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2026-03-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2026-03-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2026-03-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2026-03-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2026-03-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2026-04-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2026-04-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2026-04-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2026-04-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2026-04-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2026-04-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2026-04-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2026-05-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2026-05-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2026-05-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2026-05-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2026-05-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2026-05-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2026-05-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2026-06-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2026-06-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2026-06-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2026-06-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2026-06-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2026-06-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2026-06-01 | Architect | 40 | 0.25
P011 | ERP Implementation | 2026-07-01 | Software Developer | 320 | 2
P011 | ERP Implementation | 2026-07-01 | QA / Tester | 160 | 1
P011 | ERP Implementation | 2026-07-01 | Scrum Master | 80 | 0.5
P011 | ERP Implementation | 2026-07-01 | Product Owner | 160 | 1
P011 | ERP Implementation | 2026-07-01 | UX/UI Designer | 80 | 0.5
P011 | ERP Implementation | 2026-07-01 | DevOps Engineer | 40 | 0.25
P011 | ERP Implementation | 2026-07-01 | Architect | 40 | 0.25

## All_Projects
ProjectID | ProjectName | Status | DurationDays | Start_Date | End_Date
P005 | Cybersecurity Upgrade | In progress | 283 | 2025-04-10 | 2026-01-18
P001 | Mobile Banking App | In progress | 359 | 2025-04-13 | 2026-04-07
P003 | Data Warehouse Build | In progress | 301 | 2025-04-13 | 2026-02-08
P002 | CRM Upgrade | In progress | 251 | 2025-04-17 | 2025-12-24
P006 | E-commerce Platform | In progress | 232 | 2025-05-30 | 2026-01-17
P016 | Digital Workspace | In progress | 197 | 2025-06-16 | 2025-12-30
P011 | ERP Implementation | In progress | 399 | 2025-06-19 | 2026-07-23
P014 | AI-driven CRM | Planned | 243 | 2025-09-01 | 2026-05-02
P018 | Legacy System Migration | Planned | 382 | 2025-12-25 | 2027-01-11
P012 | Analytics Dashboard | Planned | 369 | 2025-12-28 | 2027-01-01
P015 | DevOps Automation | Planned | 269 | 2025-12-29 | 2026-09-24
P009 | HR System Upgrade | Planned | 314 | 2026-01-19 | 2026-11-29
P017 | Customer Portal | In Sales process | 201 | 2026-01-19 | 2026-08-08
P004 | AI Chatbot | In Sales process | 193 | 2026-02-11 | 2026-08-23
P019 | ML Recommendation Engine | Planned | 230 | 2026-05-03 | 2026-12-19
P010 | Mobile App Revamp | Planned | 217 | 2026-05-06 | 2026-12-09
P007 | Cloud Migration | Planned | 228 | 2026-05-07 | 2026-12-21
P020 | Data Governance Framework | Planned | 271 | 2026-05-09 | 2027-02-04
P008 | IoT Pilot | In Sales process | 187 | 2026-08-26 | 2027-03-01
P013 | Blockchain PoC | Planned | 200 | 2026-09-25 | 2027-04-13

## ResourceAssignments
Month | ProjectID | Role | ResourceID | HoursAssigned | ProjectName | ResMonthHours | AllocationPctOfResourceMonth | Name | MonthlyWageUSD | CostUSD
2025-04-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-04-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-04-01 | P002 | Architect | RES23 | 20 | CRM Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-04-01 | P002 | Architect | RES24 | 20 | CRM Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-04-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-04-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-04-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-04-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-04-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-04-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-04-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-04-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-04-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-04-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-04-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-04-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-04-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-04-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-04-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-04-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-04-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-04-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-04-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-04-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-04-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-04-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-04-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-04-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-04-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-04-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-04-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-04-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-04-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-04-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-04-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-04-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-04-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-04-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-04-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-04-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-04-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-04-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-04-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-04-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-04-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-04-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-04-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-04-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-04-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-04-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-04-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-04-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-04-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-04-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-04-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-04-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-04-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-04-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-04-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-04-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-04-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-04-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-04-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-04-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-04-01 | P002 | Scrum Master | RES13 | 20 | CRM Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-04-01 | P002 | Scrum Master | RES14 | 20 | CRM Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-04-01 | P002 | Scrum Master | RES15 | 20 | CRM Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-04-01 | P002 | Scrum Master | RES16 | 20 | CRM Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-04-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-04-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-04-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-04-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-04-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-04-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-04-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-04-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-04-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-04-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-04-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2025-04-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-04-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-04-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-04-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-04-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-04-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-04-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-04-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-04-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-04-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-04-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-04-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-04-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-04-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-04-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-04-01 | P002 | Software Developer | RES03 | 20 | CRM Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-04-01 | P002 | Software Developer | RES04 | 20 | CRM Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2025-04-01 | P002 | Software Developer | RES05 | 20 | CRM Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-04-01 | P002 | Software Developer | RES06 | 20 | CRM Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-04-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-04-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-04-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-04-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-04-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-04-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-04-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-04-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-04-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-04-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-04-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-04-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-04-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-04-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-04-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-04-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2025-04-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-04-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-04-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-04-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-04-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-04-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-04-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-04-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-04-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-04-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-04-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-04-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-04-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-04-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-05-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-05-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-05-01 | P002 | Architect | RES23 | 20 | CRM Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-05-01 | P002 | Architect | RES24 | 20 | CRM Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-05-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-05-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-05-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-05-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-05-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-05-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-05-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-05-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-05-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-05-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-05-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-05-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-05-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-05-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-05-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-05-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-05-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-05-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-05-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-05-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-05-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-05-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-05-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-05-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-05-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-05-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-05-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-05-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-05-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-05-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-05-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-05-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-05-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-05-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-05-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-05-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-05-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-05-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-05-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-05-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-05-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-05-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-05-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-05-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-05-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-05-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-05-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-05-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-05-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-05-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-05-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-05-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-05-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-05-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-05-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-05-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-05-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-05-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-05-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-05-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-05-01 | P002 | Scrum Master | RES13 | 20 | CRM Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-05-01 | P002 | Scrum Master | RES14 | 20 | CRM Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-05-01 | P002 | Scrum Master | RES15 | 20 | CRM Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-05-01 | P002 | Scrum Master | RES16 | 20 | CRM Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-05-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-05-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-05-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-05-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-05-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-05-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-05-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-05-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-05-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-05-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-05-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2025-05-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-05-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-05-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-05-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-05-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-05-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-05-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-05-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-05-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-05-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-05-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-05-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-05-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-05-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-05-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-05-01 | P002 | Software Developer | RES03 | 20 | CRM Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-05-01 | P002 | Software Developer | RES04 | 20 | CRM Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2025-05-01 | P002 | Software Developer | RES05 | 20 | CRM Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-05-01 | P002 | Software Developer | RES06 | 20 | CRM Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-05-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-05-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-05-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-05-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-05-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-05-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-05-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-05-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-05-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-05-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-05-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-05-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-05-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-05-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-05-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-05-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2025-05-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-05-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-05-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-05-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-05-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-05-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-05-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-05-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-05-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-05-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-05-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-05-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-05-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-05-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-06-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-06-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-06-01 | P002 | Architect | RES23 | 20 | CRM Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-06-01 | P002 | Architect | RES24 | 20 | CRM Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-06-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-06-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-06-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-06-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-06-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-06-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-06-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-06-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-06-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-06-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-06-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-06-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-06-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-06-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-06-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-06-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-06-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-06-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-06-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-06-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-06-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-06-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-06-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-06-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-06-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-06-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-06-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-06-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-06-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-06-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-06-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-06-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-06-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-06-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-06-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-06-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-06-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-06-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-06-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-06-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-06-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-06-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-06-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-06-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-06-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-06-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-06-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-06-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-06-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-06-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-06-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-06-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-06-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-06-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-06-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-06-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-06-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-06-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-06-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-06-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-06-01 | P002 | Scrum Master | RES13 | 20 | CRM Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-06-01 | P002 | Scrum Master | RES14 | 20 | CRM Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-06-01 | P002 | Scrum Master | RES15 | 20 | CRM Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-06-01 | P002 | Scrum Master | RES16 | 20 | CRM Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-06-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-06-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-06-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-06-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-06-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-06-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-06-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-06-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-06-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-06-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-06-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2025-06-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-06-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-06-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-06-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-06-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-06-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-06-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-06-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-06-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-06-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-06-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-06-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-06-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-06-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-06-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-06-01 | P002 | Software Developer | RES03 | 20 | CRM Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-06-01 | P002 | Software Developer | RES04 | 20 | CRM Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2025-06-01 | P002 | Software Developer | RES05 | 20 | CRM Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-06-01 | P002 | Software Developer | RES06 | 20 | CRM Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-06-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-06-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-06-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-06-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-06-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-06-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-06-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-06-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-06-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-06-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-06-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-06-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-06-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-06-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-06-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-06-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2025-06-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-06-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-06-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-06-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-06-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-06-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-06-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-06-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-06-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-06-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-06-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-06-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-06-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-06-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-07-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-07-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-07-01 | P002 | Architect | RES23 | 20 | CRM Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-07-01 | P002 | Architect | RES24 | 20 | CRM Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-07-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-07-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-07-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-07-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-07-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-07-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-07-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-07-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-07-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-07-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-07-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-07-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-07-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-07-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-07-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-07-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-07-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-07-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-07-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-07-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-07-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-07-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-07-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-07-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-07-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-07-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-07-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-07-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-07-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-07-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-07-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-07-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-07-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-07-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-07-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-07-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-07-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-07-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-07-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-07-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-07-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-07-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-07-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-07-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-07-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-07-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-07-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-07-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-07-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-07-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-07-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-07-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-07-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-07-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-07-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-07-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-07-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-07-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-07-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-07-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-07-01 | P002 | Scrum Master | RES13 | 20 | CRM Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-07-01 | P002 | Scrum Master | RES14 | 20 | CRM Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-07-01 | P002 | Scrum Master | RES15 | 20 | CRM Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-07-01 | P002 | Scrum Master | RES16 | 20 | CRM Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-07-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-07-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-07-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-07-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-07-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-07-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-07-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-07-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-07-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-07-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-07-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2025-07-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-07-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-07-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-07-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-07-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-07-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-07-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-07-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-07-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-07-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-07-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-07-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-07-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-07-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-07-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-07-01 | P002 | Software Developer | RES03 | 20 | CRM Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-07-01 | P002 | Software Developer | RES04 | 20 | CRM Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2025-07-01 | P002 | Software Developer | RES05 | 20 | CRM Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-07-01 | P002 | Software Developer | RES06 | 20 | CRM Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-07-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-07-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-07-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-07-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-07-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-07-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-07-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-07-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-07-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-07-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-07-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-07-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-07-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-07-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-07-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-07-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2025-07-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-07-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-07-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-07-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-07-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-07-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-07-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-07-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-07-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-07-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-07-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-07-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-07-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-07-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-08-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-08-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-08-01 | P002 | Architect | RES23 | 20 | CRM Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-08-01 | P002 | Architect | RES24 | 20 | CRM Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-08-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-08-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-08-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-08-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-08-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-08-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-08-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-08-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-08-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-08-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-08-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-08-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-08-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-08-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-08-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-08-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-08-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-08-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-08-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-08-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-08-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-08-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-08-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-08-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-08-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-08-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-08-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-08-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-08-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-08-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-08-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-08-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-08-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-08-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-08-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-08-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-08-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-08-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-08-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-08-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-08-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-08-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-08-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-08-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-08-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-08-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-08-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-08-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-08-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-08-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-08-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-08-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-08-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-08-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-08-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-08-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-08-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-08-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-08-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-08-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-08-01 | P002 | Scrum Master | RES13 | 20 | CRM Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-08-01 | P002 | Scrum Master | RES14 | 20 | CRM Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-08-01 | P002 | Scrum Master | RES15 | 20 | CRM Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-08-01 | P002 | Scrum Master | RES16 | 20 | CRM Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-08-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-08-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-08-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-08-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-08-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-08-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-08-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-08-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-08-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-08-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-08-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2025-08-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-08-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-08-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-08-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-08-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-08-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-08-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-08-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-08-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-08-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-08-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-08-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-08-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-08-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-08-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-08-01 | P002 | Software Developer | RES03 | 20 | CRM Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-08-01 | P002 | Software Developer | RES04 | 20 | CRM Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2025-08-01 | P002 | Software Developer | RES05 | 20 | CRM Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-08-01 | P002 | Software Developer | RES06 | 20 | CRM Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-08-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-08-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-08-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-08-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-08-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-08-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-08-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-08-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-08-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-08-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-08-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-08-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-08-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-08-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-08-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-08-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2025-08-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-08-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-08-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-08-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-08-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-08-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-08-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-08-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-08-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-08-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-08-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-08-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-08-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-08-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-09-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-09-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-09-01 | P002 | Architect | RES23 | 20 | CRM Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-09-01 | P002 | Architect | RES24 | 20 | CRM Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-09-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-09-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-09-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-09-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-09-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-09-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-09-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-09-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-09-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-09-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-09-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-09-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-09-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-09-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-09-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-09-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-09-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-09-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-09-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-09-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-09-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-09-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-09-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-09-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-09-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-09-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-09-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-09-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-09-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-09-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-09-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-09-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-09-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-09-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-09-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-09-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-09-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-09-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-09-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-09-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-09-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-09-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-09-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-09-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-09-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-09-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-09-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-09-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-09-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-09-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-09-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-09-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-09-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-09-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-09-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-09-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-09-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-09-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-09-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-09-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-09-01 | P002 | Scrum Master | RES13 | 20 | CRM Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-09-01 | P002 | Scrum Master | RES14 | 20 | CRM Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-09-01 | P002 | Scrum Master | RES15 | 20 | CRM Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-09-01 | P002 | Scrum Master | RES16 | 20 | CRM Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-09-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-09-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-09-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-09-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-09-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-09-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-09-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-09-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-09-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-09-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-09-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2025-09-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-09-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-09-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-09-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-09-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-09-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-09-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-09-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-09-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-09-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-09-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-09-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-09-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-09-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-09-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-09-01 | P002 | Software Developer | RES03 | 20 | CRM Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-09-01 | P002 | Software Developer | RES04 | 20 | CRM Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2025-09-01 | P002 | Software Developer | RES05 | 20 | CRM Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-09-01 | P002 | Software Developer | RES06 | 20 | CRM Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-09-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-09-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-09-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-09-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-09-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-09-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-09-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-09-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-09-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-09-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-09-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-09-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-09-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-09-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-09-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-09-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2025-09-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-09-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-09-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-09-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-09-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-09-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-09-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-09-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-09-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-09-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-09-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-09-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-09-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-09-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-10-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-10-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-10-01 | P002 | Architect | RES23 | 20 | CRM Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-10-01 | P002 | Architect | RES24 | 20 | CRM Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-10-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-10-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-10-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-10-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-10-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-10-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-10-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-10-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-10-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-10-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-10-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-10-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-10-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-10-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-10-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-10-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-10-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-10-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-10-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-10-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-10-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-10-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-10-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-10-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-10-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-10-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-10-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-10-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-10-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-10-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-10-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-10-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-10-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-10-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-10-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-10-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-10-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-10-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-10-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-10-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-10-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-10-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-10-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-10-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-10-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-10-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-10-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-10-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-10-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-10-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-10-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-10-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-10-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-10-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-10-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-10-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-10-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-10-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-10-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-10-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-10-01 | P002 | Scrum Master | RES13 | 20 | CRM Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-10-01 | P002 | Scrum Master | RES14 | 20 | CRM Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-10-01 | P002 | Scrum Master | RES15 | 20 | CRM Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-10-01 | P002 | Scrum Master | RES16 | 20 | CRM Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-10-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-10-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-10-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-10-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-10-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-10-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-10-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-10-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-10-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-10-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-10-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2025-10-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-10-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-10-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-10-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-10-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-10-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-10-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-10-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-10-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-10-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-10-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-10-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-10-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-10-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-10-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-10-01 | P002 | Software Developer | RES03 | 20 | CRM Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-10-01 | P002 | Software Developer | RES04 | 20 | CRM Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2025-10-01 | P002 | Software Developer | RES05 | 20 | CRM Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-10-01 | P002 | Software Developer | RES06 | 20 | CRM Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-10-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-10-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-10-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-10-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-10-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-10-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-10-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-10-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-10-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-10-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-10-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-10-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-10-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-10-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-10-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-10-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2025-10-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-10-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-10-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-10-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-10-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-10-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-10-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-10-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-10-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-10-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-10-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-10-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-10-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-10-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-11-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-11-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-11-01 | P002 | Architect | RES23 | 20 | CRM Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-11-01 | P002 | Architect | RES24 | 20 | CRM Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-11-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-11-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-11-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-11-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-11-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-11-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-11-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-11-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-11-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-11-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-11-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-11-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-11-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-11-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-11-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-11-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-11-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-11-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-11-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-11-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-11-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-11-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-11-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-11-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-11-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-11-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-11-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-11-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-11-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-11-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-11-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-11-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-11-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-11-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-11-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-11-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-11-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-11-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-11-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-11-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-11-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-11-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-11-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-11-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-11-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-11-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-11-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-11-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-11-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-11-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-11-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-11-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-11-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-11-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-11-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-11-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-11-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-11-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-11-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-11-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-11-01 | P002 | Scrum Master | RES13 | 20 | CRM Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-11-01 | P002 | Scrum Master | RES14 | 20 | CRM Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-11-01 | P002 | Scrum Master | RES15 | 20 | CRM Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-11-01 | P002 | Scrum Master | RES16 | 20 | CRM Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-11-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-11-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-11-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-11-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-11-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-11-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-11-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-11-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-11-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-11-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-11-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2025-11-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-11-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-11-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-11-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-11-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-11-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-11-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-11-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-11-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-11-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-11-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-11-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-11-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-11-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-11-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-11-01 | P002 | Software Developer | RES03 | 20 | CRM Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-11-01 | P002 | Software Developer | RES04 | 20 | CRM Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2025-11-01 | P002 | Software Developer | RES05 | 20 | CRM Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-11-01 | P002 | Software Developer | RES06 | 20 | CRM Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-11-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-11-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-11-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-11-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-11-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-11-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-11-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-11-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-11-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-11-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-11-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-11-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-11-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-11-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-11-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-11-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2025-11-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-11-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-11-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-11-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-11-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-11-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-11-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-11-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-11-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-11-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-11-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-11-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-11-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-11-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-12-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-12-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-12-01 | P002 | Architect | RES23 | 20 | CRM Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-12-01 | P002 | Architect | RES24 | 20 | CRM Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-12-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2025-12-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2025-12-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-12-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-12-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-12-01 | P002 | DevOps Engineer | RES22 | 20 | CRM Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-12-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-12-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2025-12-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-12-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-12-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-12-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-12-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-12-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-12-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-12-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-12-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-12-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-12-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-12-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-12-01 | P002 | Product Owner | RES17 | 20 | CRM Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-12-01 | P002 | Product Owner | RES18 | 20 | CRM Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-12-01 | P002 | Product Owner | RES19 | 20 | CRM Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-12-01 | P002 | Product Owner | RES20 | 20 | CRM Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-12-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-12-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-12-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-12-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-12-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2025-12-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2025-12-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2025-12-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2025-12-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-12-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-12-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-12-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-12-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-12-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-12-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2025-12-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-12-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-12-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-12-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-12-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-12-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-12-01 | P002 | QA / Tester | RES11 | 20 | CRM Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-12-01 | P002 | QA / Tester | RES12 | 20 | CRM Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-12-01 | P002 | QA / Tester | RES10 | 20 | CRM Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2025-12-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-12-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-12-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-12-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-12-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-12-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2025-12-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2025-12-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2025-12-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-12-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-12-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-12-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-12-01 | P002 | Scrum Master | RES13 | 20 | CRM Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-12-01 | P002 | Scrum Master | RES14 | 20 | CRM Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-12-01 | P002 | Scrum Master | RES15 | 20 | CRM Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-12-01 | P002 | Scrum Master | RES16 | 20 | CRM Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-12-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2025-12-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2025-12-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2025-12-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2025-12-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-12-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-12-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-12-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-12-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-12-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-12-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2025-12-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-12-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-12-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-12-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-12-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2025-12-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-12-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2025-12-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-12-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-12-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-12-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-12-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-12-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-12-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-12-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-12-01 | P002 | Software Developer | RES03 | 20 | CRM Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-12-01 | P002 | Software Developer | RES04 | 20 | CRM Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2025-12-01 | P002 | Software Developer | RES05 | 20 | CRM Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-12-01 | P002 | Software Developer | RES06 | 20 | CRM Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-12-01 | P002 | Software Developer | RES07 | 20 | CRM Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2025-12-01 | P002 | Software Developer | RES08 | 20 | CRM Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-12-01 | P002 | Software Developer | RES09 | 20 | CRM Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-12-01 | P002 | Software Developer | RES25 | 20 | CRM Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-12-01 | P002 | Software Developer | RES01 | 20 | CRM Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-12-01 | P002 | Software Developer | RES02 | 20 | CRM Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2025-12-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-12-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-12-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-12-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-12-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-12-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-12-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2025-12-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2025-12-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2025-12-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2025-12-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2025-12-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2025-12-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2025-12-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2025-12-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2025-12-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2025-12-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-12-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-12-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-12-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-12-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-12-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-12-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2025-12-01 | P002 | UX/UI Designer | RES21 | 20 | CRM Upgrade | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-01-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2026-01-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2026-01-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2026-01-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2026-01-01 | P005 | Architect | RES23 | 20 | Cybersecurity Upgrade | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2026-01-01 | P005 | Architect | RES24 | 20 | Cybersecurity Upgrade | 60 | 0.3333 | Victor Hall | 8200 | 1025
2026-01-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-01-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-01-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-01-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-01-01 | P005 | DevOps Engineer | RES22 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-01-01 | P005 | DevOps Engineer | RES22 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-01-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-01-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-01-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-01-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-01-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-01-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-01-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-01-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-01-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-01-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-01-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-01-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-01-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-01-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-01-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-01-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-01-01 | P005 | Product Owner | RES17 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-01-01 | P005 | Product Owner | RES18 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-01-01 | P005 | Product Owner | RES19 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-01-01 | P005 | Product Owner | RES20 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-01-01 | P005 | Product Owner | RES17 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-01-01 | P005 | Product Owner | RES18 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-01-01 | P005 | Product Owner | RES19 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-01-01 | P005 | Product Owner | RES20 | 20 | Cybersecurity Upgrade | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-01-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2026-01-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-01-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-01-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2026-01-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-01-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-01-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2026-01-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-01-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-01-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2026-01-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-01-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-01-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2026-01-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-01-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-01-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2026-01-01 | P005 | QA / Tester | RES11 | 20 | Cybersecurity Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-01-01 | P005 | QA / Tester | RES12 | 20 | Cybersecurity Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-01-01 | P005 | QA / Tester | RES10 | 20 | Cybersecurity Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2026-01-01 | P005 | QA / Tester | RES11 | 20 | Cybersecurity Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-01-01 | P005 | QA / Tester | RES12 | 20 | Cybersecurity Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-01-01 | P005 | QA / Tester | RES10 | 20 | Cybersecurity Upgrade | 160 | 0.125 | George Clark | 5000 | 625
2026-01-01 | P005 | QA / Tester | RES11 | 20 | Cybersecurity Upgrade | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-01-01 | P005 | QA / Tester | RES12 | 20 | Cybersecurity Upgrade | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-01-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2026-01-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2026-01-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2026-01-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2026-01-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2026-01-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2026-01-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2026-01-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2026-01-01 | P005 | Scrum Master | RES13 | 20 | Cybersecurity Upgrade | 60 | 0.3333 | Julia Carter | 7000 | 875
2026-01-01 | P005 | Scrum Master | RES14 | 20 | Cybersecurity Upgrade | 60 | 0.3333 | Kevin Turner | 7200 | 900
2026-01-01 | P005 | Scrum Master | RES15 | 20 | Cybersecurity Upgrade | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2026-01-01 | P005 | Scrum Master | RES16 | 20 | Cybersecurity Upgrade | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2026-01-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-01-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2026-01-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-01-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2026-01-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-01-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-01-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2026-01-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-01-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2026-01-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2026-01-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-01-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2026-01-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-01-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2026-01-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-01-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-01-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2026-01-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-01-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2026-01-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2026-01-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-01-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2026-01-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-01-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2026-01-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-01-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-01-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2026-01-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-01-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2026-01-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2026-01-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-01-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2026-01-01 | P005 | Software Developer | RES03 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-01-01 | P005 | Software Developer | RES04 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2026-01-01 | P005 | Software Developer | RES05 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-01-01 | P005 | Software Developer | RES06 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-01-01 | P005 | Software Developer | RES07 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2026-01-01 | P005 | Software Developer | RES08 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-01-01 | P005 | Software Developer | RES09 | 20 | Cybersecurity Upgrade | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2026-01-01 | P005 | Software Developer | RES25 | 20 | Cybersecurity Upgrade | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2026-01-01 | P005 | Software Developer | RES01 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-01-01 | P005 | Software Developer | RES02 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Bob Smith | 6200 | 775
2026-01-01 | P005 | Software Developer | RES03 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-01-01 | P005 | Software Developer | RES04 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Diana Miller | 6800 | 850
2026-01-01 | P005 | Software Developer | RES05 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-01-01 | P005 | Software Developer | RES06 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-01-01 | P005 | Software Developer | RES07 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Henry Collins | 6600 | 825
2026-01-01 | P005 | Software Developer | RES08 | 20 | Cybersecurity Upgrade | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-01-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-01-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-01-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-01-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-01-01 | P003 | UX/UI Designer | RES21 | 20 | Data Warehouse Build | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-01-01 | P003 | UX/UI Designer | RES21 | 20 | Data Warehouse Build | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-01-01 | P003 | UX/UI Designer | RES21 | 20 | Data Warehouse Build | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-01-01 | P003 | UX/UI Designer | RES21 | 20 | Data Warehouse Build | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-02-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2026-02-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 60 | 0.3333 | Victor Hall | 8200 | 1025
2026-02-01 | P003 | Architect | RES23 | 20 | Data Warehouse Build | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2026-02-01 | P003 | Architect | RES24 | 20 | Data Warehouse Build | 60 | 0.3333 | Victor Hall | 8200 | 1025
2026-02-01 | P011 | Architect | RES23 | 20 | ERP Implementation | 60 | 0.3333 | Tina Murphy | 8000 | 1000
2026-02-01 | P011 | Architect | RES24 | 20 | ERP Implementation | 60 | 0.3333 | Victor Hall | 8200 | 1025
2026-02-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-02-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-02-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-02-01 | P003 | DevOps Engineer | RES22 | 20 | Data Warehouse Build | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-02-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-02-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 120 | 0.1667 | Samuel Bennett | 6800 | 850
2026-02-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-02-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-02-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-02-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-02-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-02-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-02-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-02-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-02-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-02-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-02-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-02-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-02-01 | P003 | Product Owner | RES17 | 20 | Data Warehouse Build | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-02-01 | P003 | Product Owner | RES18 | 20 | Data Warehouse Build | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-02-01 | P003 | Product Owner | RES19 | 20 | Data Warehouse Build | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-02-01 | P003 | Product Owner | RES20 | 20 | Data Warehouse Build | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-02-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-02-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-02-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-02-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-02-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 120 | 0.1667 | Natalie Perez | 7500 | 937.5
2026-02-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 120 | 0.1667 | Oliver Scott | 7600 | 950
2026-02-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 120 | 0.1667 | Paula Edwards | 7400 | 925
2026-02-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 120 | 0.1667 | Quentin Hughes | 7700 | 962.5
2026-02-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2026-02-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-02-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-02-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2026-02-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-02-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-02-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 160 | 0.125 | George Clark | 5000 | 625
2026-02-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-02-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-02-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2026-02-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-02-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-02-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2026-02-01 | P003 | QA / Tester | RES11 | 20 | Data Warehouse Build | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-02-01 | P003 | QA / Tester | RES12 | 20 | Data Warehouse Build | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-02-01 | P003 | QA / Tester | RES10 | 20 | Data Warehouse Build | 160 | 0.125 | George Clark | 5000 | 625
2026-02-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-02-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-02-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 160 | 0.125 | George Clark | 5000 | 625
2026-02-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-02-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-02-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 160 | 0.125 | George Clark | 5000 | 625
2026-02-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 160 | 0.125 | Hannah Lopez | 5200 | 650
2026-02-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 160 | 0.125 | Ian Martinez | 5100 | 637.5
2026-02-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 60 | 0.3333 | Julia Carter | 7000 | 875
2026-02-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 60 | 0.3333 | Kevin Turner | 7200 | 900
2026-02-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2026-02-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2026-02-01 | P003 | Scrum Master | RES13 | 20 | Data Warehouse Build | 60 | 0.3333 | Julia Carter | 7000 | 875
2026-02-01 | P003 | Scrum Master | RES14 | 20 | Data Warehouse Build | 60 | 0.3333 | Kevin Turner | 7200 | 900
2026-02-01 | P003 | Scrum Master | RES15 | 20 | Data Warehouse Build | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2026-02-01 | P003 | Scrum Master | RES16 | 20 | Data Warehouse Build | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2026-02-01 | P011 | Scrum Master | RES13 | 20 | ERP Implementation | 60 | 0.3333 | Julia Carter | 7000 | 875
2026-02-01 | P011 | Scrum Master | RES14 | 20 | ERP Implementation | 60 | 0.3333 | Kevin Turner | 7200 | 900
2026-02-01 | P011 | Scrum Master | RES15 | 20 | ERP Implementation | 60 | 0.3333 | Laura Adams | 7100 | 887.5
2026-02-01 | P011 | Scrum Master | RES16 | 20 | ERP Implementation | 60 | 0.3333 | Mark Robinson | 7300 | 912.5
2026-02-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-02-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2026-02-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-02-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2026-02-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-02-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-02-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 100 | 0.2 | Henry Collins | 6600 | 825
2026-02-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-02-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2026-02-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2026-02-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-02-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 100 | 0.2 | Bob Smith | 6200 | 775
2026-02-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-02-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 100 | 0.2 | Diana Miller | 6800 | 850
2026-02-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-02-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-02-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2026-02-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-02-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2026-02-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2026-02-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-02-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2026-02-01 | P003 | Software Developer | RES03 | 20 | Data Warehouse Build | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-02-01 | P003 | Software Developer | RES04 | 20 | Data Warehouse Build | 100 | 0.2 | Diana Miller | 6800 | 850
2026-02-01 | P003 | Software Developer | RES05 | 20 | Data Warehouse Build | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-02-01 | P003 | Software Developer | RES06 | 20 | Data Warehouse Build | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-02-01 | P003 | Software Developer | RES07 | 20 | Data Warehouse Build | 100 | 0.2 | Henry Collins | 6600 | 825
2026-02-01 | P003 | Software Developer | RES08 | 20 | Data Warehouse Build | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-02-01 | P003 | Software Developer | RES09 | 20 | Data Warehouse Build | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2026-02-01 | P003 | Software Developer | RES25 | 20 | Data Warehouse Build | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2026-02-01 | P003 | Software Developer | RES01 | 20 | Data Warehouse Build | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-02-01 | P003 | Software Developer | RES02 | 20 | Data Warehouse Build | 100 | 0.2 | Bob Smith | 6200 | 775
2026-02-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-02-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 100 | 0.2 | Diana Miller | 6800 | 850
2026-02-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-02-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-02-01 | P011 | Software Developer | RES07 | 20 | ERP Implementation | 100 | 0.2 | Henry Collins | 6600 | 825
2026-02-01 | P011 | Software Developer | RES08 | 20 | ERP Implementation | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-02-01 | P011 | Software Developer | RES09 | 20 | ERP Implementation | 80 | 0.25 | Jack Thompson | 6450 | 806.25
2026-02-01 | P011 | Software Developer | RES25 | 20 | ERP Implementation | 80 | 0.25 | Wendy Brooks | 6550 | 818.75
2026-02-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 100 | 0.2 | Alice Johnson | 6000 | 750
2026-02-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 100 | 0.2 | Bob Smith | 6200 | 775
2026-02-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 100 | 0.2 | Charlie Brown | 6500 | 812.5
2026-02-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 100 | 0.2 | Diana Miller | 6800 | 850
2026-02-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 100 | 0.2 | Ethan Davis | 6400 | 800
2026-02-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 100 | 0.2 | Fiona Wilson | 6300 | 787.5
2026-02-01 | P011 | Software Developer | RES07 | 20 | ERP Implementation | 100 | 0.2 | Henry Collins | 6600 | 825
2026-02-01 | P011 | Software Developer | RES08 | 20 | ERP Implementation | 100 | 0.2 | Isabella Wright | 6700 | 837.5
2026-02-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-02-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-02-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-02-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-02-01 | P003 | UX/UI Designer | RES21 | 20 | Data Warehouse Build | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-02-01 | P003 | UX/UI Designer | RES21 | 20 | Data Warehouse Build | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-02-01 | P003 | UX/UI Designer | RES21 | 20 | Data Warehouse Build | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-02-01 | P003 | UX/UI Designer | RES21 | 20 | Data Warehouse Build | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-03-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 40 | 0.5 | Tina Murphy | 8000 | 1000
2026-03-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 40 | 0.5 | Victor Hall | 8200 | 1025
2026-03-01 | P011 | Architect | RES23 | 20 | ERP Implementation | 40 | 0.5 | Tina Murphy | 8000 | 1000
2026-03-01 | P011 | Architect | RES24 | 20 | ERP Implementation | 40 | 0.5 | Victor Hall | 8200 | 1025
2026-03-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 80 | 0.25 | Samuel Bennett | 6800 | 850
2026-03-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 80 | 0.25 | Samuel Bennett | 6800 | 850
2026-03-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 80 | 0.25 | Samuel Bennett | 6800 | 850
2026-03-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 80 | 0.25 | Samuel Bennett | 6800 | 850
2026-03-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 80 | 0.25 | Natalie Perez | 7500 | 937.5
2026-03-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 80 | 0.25 | Oliver Scott | 7600 | 950
2026-03-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 80 | 0.25 | Paula Edwards | 7400 | 925
2026-03-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 80 | 0.25 | Quentin Hughes | 7700 | 962.5
2026-03-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 80 | 0.25 | Natalie Perez | 7500 | 937.5
2026-03-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 80 | 0.25 | Oliver Scott | 7600 | 950
2026-03-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 80 | 0.25 | Paula Edwards | 7400 | 925
2026-03-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 80 | 0.25 | Quentin Hughes | 7700 | 962.5
2026-03-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 80 | 0.25 | Natalie Perez | 7500 | 937.5
2026-03-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 80 | 0.25 | Oliver Scott | 7600 | 950
2026-03-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 80 | 0.25 | Paula Edwards | 7400 | 925
2026-03-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 80 | 0.25 | Quentin Hughes | 7700 | 962.5
2026-03-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 80 | 0.25 | Natalie Perez | 7500 | 937.5
2026-03-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 80 | 0.25 | Oliver Scott | 7600 | 950
2026-03-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 80 | 0.25 | Paula Edwards | 7400 | 925
2026-03-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 80 | 0.25 | Quentin Hughes | 7700 | 962.5
2026-03-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 120 | 0.1667 | George Clark | 5000 | 625
2026-03-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-03-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-03-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 120 | 0.1667 | George Clark | 5000 | 625
2026-03-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-03-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-03-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 120 | 0.1667 | George Clark | 5000 | 625
2026-03-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-03-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-03-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 120 | 0.1667 | George Clark | 5000 | 625
2026-03-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-03-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-03-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 120 | 0.1667 | George Clark | 5000 | 625
2026-03-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-03-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-03-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 120 | 0.1667 | George Clark | 5000 | 625
2026-03-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 40 | 0.5 | Julia Carter | 7000 | 875
2026-03-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 40 | 0.5 | Kevin Turner | 7200 | 900
2026-03-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 40 | 0.5 | Laura Adams | 7100 | 887.5
2026-03-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 40 | 0.5 | Mark Robinson | 7300 | 912.5
2026-03-01 | P011 | Scrum Master | RES13 | 20 | ERP Implementation | 40 | 0.5 | Julia Carter | 7000 | 875
2026-03-01 | P011 | Scrum Master | RES14 | 20 | ERP Implementation | 40 | 0.5 | Kevin Turner | 7200 | 900
2026-03-01 | P011 | Scrum Master | RES15 | 20 | ERP Implementation | 40 | 0.5 | Laura Adams | 7100 | 887.5
2026-03-01 | P011 | Scrum Master | RES16 | 20 | ERP Implementation | 40 | 0.5 | Mark Robinson | 7300 | 912.5
2026-03-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 80 | 0.25 | Alice Johnson | 6000 | 750
2026-03-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 80 | 0.25 | Bob Smith | 6200 | 775
2026-03-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 60 | 0.3333 | Charlie Brown | 6500 | 812.5
2026-03-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 60 | 0.3333 | Diana Miller | 6800 | 850
2026-03-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 60 | 0.3333 | Ethan Davis | 6400 | 800
2026-03-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 60 | 0.3333 | Fiona Wilson | 6300 | 787.5
2026-03-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 60 | 0.3333 | Henry Collins | 6600 | 825
2026-03-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 60 | 0.3333 | Isabella Wright | 6700 | 837.5
2026-03-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 60 | 0.3333 | Jack Thompson | 6450 | 806.25
2026-03-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 60 | 0.3333 | Wendy Brooks | 6550 | 818.75
2026-03-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 80 | 0.25 | Alice Johnson | 6000 | 750
2026-03-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 80 | 0.25 | Bob Smith | 6200 | 775
2026-03-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 60 | 0.3333 | Charlie Brown | 6500 | 812.5
2026-03-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 60 | 0.3333 | Diana Miller | 6800 | 850
2026-03-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 60 | 0.3333 | Ethan Davis | 6400 | 800
2026-03-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 60 | 0.3333 | Fiona Wilson | 6300 | 787.5
2026-03-01 | P011 | Software Developer | RES07 | 20 | ERP Implementation | 60 | 0.3333 | Henry Collins | 6600 | 825
2026-03-01 | P011 | Software Developer | RES08 | 20 | ERP Implementation | 60 | 0.3333 | Isabella Wright | 6700 | 837.5
2026-03-01 | P011 | Software Developer | RES09 | 20 | ERP Implementation | 60 | 0.3333 | Jack Thompson | 6450 | 806.25
2026-03-01 | P011 | Software Developer | RES25 | 20 | ERP Implementation | 60 | 0.3333 | Wendy Brooks | 6550 | 818.75
2026-03-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 80 | 0.25 | Alice Johnson | 6000 | 750
2026-03-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 80 | 0.25 | Bob Smith | 6200 | 775
2026-03-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 60 | 0.3333 | Charlie Brown | 6500 | 812.5
2026-03-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 60 | 0.3333 | Diana Miller | 6800 | 850
2026-03-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 60 | 0.3333 | Ethan Davis | 6400 | 800
2026-03-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 60 | 0.3333 | Fiona Wilson | 6300 | 787.5
2026-03-01 | P011 | Software Developer | RES07 | 20 | ERP Implementation | 60 | 0.3333 | Henry Collins | 6600 | 825
2026-03-01 | P011 | Software Developer | RES08 | 20 | ERP Implementation | 60 | 0.3333 | Isabella Wright | 6700 | 837.5
2026-03-01 | P011 | Software Developer | RES09 | 20 | ERP Implementation | 60 | 0.3333 | Jack Thompson | 6450 | 806.25
2026-03-01 | P011 | Software Developer | RES25 | 20 | ERP Implementation | 60 | 0.3333 | Wendy Brooks | 6550 | 818.75
2026-03-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 80 | 0.25 | Alice Johnson | 6000 | 750
2026-03-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 80 | 0.25 | Bob Smith | 6200 | 775
2026-03-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-03-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-03-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-03-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-03-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-03-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-03-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-03-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-04-01 | P001 | Architect | RES23 | 20 | Mobile Banking App | 40 | 0.5 | Tina Murphy | 8000 | 1000
2026-04-01 | P001 | Architect | RES24 | 20 | Mobile Banking App | 40 | 0.5 | Victor Hall | 8200 | 1025
2026-04-01 | P011 | Architect | RES23 | 20 | ERP Implementation | 40 | 0.5 | Tina Murphy | 8000 | 1000
2026-04-01 | P011 | Architect | RES24 | 20 | ERP Implementation | 40 | 0.5 | Victor Hall | 8200 | 1025
2026-04-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 80 | 0.25 | Samuel Bennett | 6800 | 850
2026-04-01 | P001 | DevOps Engineer | RES22 | 20 | Mobile Banking App | 80 | 0.25 | Samuel Bennett | 6800 | 850
2026-04-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 80 | 0.25 | Samuel Bennett | 6800 | 850
2026-04-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 80 | 0.25 | Samuel Bennett | 6800 | 850
2026-04-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 80 | 0.25 | Natalie Perez | 7500 | 937.5
2026-04-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 80 | 0.25 | Oliver Scott | 7600 | 950
2026-04-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 80 | 0.25 | Paula Edwards | 7400 | 925
2026-04-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 80 | 0.25 | Quentin Hughes | 7700 | 962.5
2026-04-01 | P001 | Product Owner | RES17 | 20 | Mobile Banking App | 80 | 0.25 | Natalie Perez | 7500 | 937.5
2026-04-01 | P001 | Product Owner | RES18 | 20 | Mobile Banking App | 80 | 0.25 | Oliver Scott | 7600 | 950
2026-04-01 | P001 | Product Owner | RES19 | 20 | Mobile Banking App | 80 | 0.25 | Paula Edwards | 7400 | 925
2026-04-01 | P001 | Product Owner | RES20 | 20 | Mobile Banking App | 80 | 0.25 | Quentin Hughes | 7700 | 962.5
2026-04-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 80 | 0.25 | Natalie Perez | 7500 | 937.5
2026-04-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 80 | 0.25 | Oliver Scott | 7600 | 950
2026-04-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 80 | 0.25 | Paula Edwards | 7400 | 925
2026-04-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 80 | 0.25 | Quentin Hughes | 7700 | 962.5
2026-04-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 80 | 0.25 | Natalie Perez | 7500 | 937.5
2026-04-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 80 | 0.25 | Oliver Scott | 7600 | 950
2026-04-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 80 | 0.25 | Paula Edwards | 7400 | 925
2026-04-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 80 | 0.25 | Quentin Hughes | 7700 | 962.5
2026-04-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 120 | 0.1667 | George Clark | 5000 | 625
2026-04-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-04-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-04-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 120 | 0.1667 | George Clark | 5000 | 625
2026-04-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-04-01 | P001 | QA / Tester | RES12 | 20 | Mobile Banking App | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-04-01 | P001 | QA / Tester | RES10 | 20 | Mobile Banking App | 120 | 0.1667 | George Clark | 5000 | 625
2026-04-01 | P001 | QA / Tester | RES11 | 20 | Mobile Banking App | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-04-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-04-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 120 | 0.1667 | George Clark | 5000 | 625
2026-04-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-04-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-04-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 120 | 0.1667 | George Clark | 5000 | 625
2026-04-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 100 | 0.2 | Hannah Lopez | 5200 | 650
2026-04-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 100 | 0.2 | Ian Martinez | 5100 | 637.5
2026-04-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 120 | 0.1667 | George Clark | 5000 | 625
2026-04-01 | P001 | Scrum Master | RES13 | 20 | Mobile Banking App | 40 | 0.5 | Julia Carter | 7000 | 875
2026-04-01 | P001 | Scrum Master | RES14 | 20 | Mobile Banking App | 40 | 0.5 | Kevin Turner | 7200 | 900
2026-04-01 | P001 | Scrum Master | RES15 | 20 | Mobile Banking App | 40 | 0.5 | Laura Adams | 7100 | 887.5
2026-04-01 | P001 | Scrum Master | RES16 | 20 | Mobile Banking App | 40 | 0.5 | Mark Robinson | 7300 | 912.5
2026-04-01 | P011 | Scrum Master | RES13 | 20 | ERP Implementation | 40 | 0.5 | Julia Carter | 7000 | 875
2026-04-01 | P011 | Scrum Master | RES14 | 20 | ERP Implementation | 40 | 0.5 | Kevin Turner | 7200 | 900
2026-04-01 | P011 | Scrum Master | RES15 | 20 | ERP Implementation | 40 | 0.5 | Laura Adams | 7100 | 887.5
2026-04-01 | P011 | Scrum Master | RES16 | 20 | ERP Implementation | 40 | 0.5 | Mark Robinson | 7300 | 912.5
2026-04-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 80 | 0.25 | Alice Johnson | 6000 | 750
2026-04-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 80 | 0.25 | Bob Smith | 6200 | 775
2026-04-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 60 | 0.3333 | Charlie Brown | 6500 | 812.5
2026-04-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 60 | 0.3333 | Diana Miller | 6800 | 850
2026-04-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 60 | 0.3333 | Ethan Davis | 6400 | 800
2026-04-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 60 | 0.3333 | Fiona Wilson | 6300 | 787.5
2026-04-01 | P001 | Software Developer | RES07 | 20 | Mobile Banking App | 60 | 0.3333 | Henry Collins | 6600 | 825
2026-04-01 | P001 | Software Developer | RES08 | 20 | Mobile Banking App | 60 | 0.3333 | Isabella Wright | 6700 | 837.5
2026-04-01 | P001 | Software Developer | RES09 | 20 | Mobile Banking App | 60 | 0.3333 | Jack Thompson | 6450 | 806.25
2026-04-01 | P001 | Software Developer | RES25 | 20 | Mobile Banking App | 60 | 0.3333 | Wendy Brooks | 6550 | 818.75
2026-04-01 | P001 | Software Developer | RES01 | 20 | Mobile Banking App | 80 | 0.25 | Alice Johnson | 6000 | 750
2026-04-01 | P001 | Software Developer | RES02 | 20 | Mobile Banking App | 80 | 0.25 | Bob Smith | 6200 | 775
2026-04-01 | P001 | Software Developer | RES03 | 20 | Mobile Banking App | 60 | 0.3333 | Charlie Brown | 6500 | 812.5
2026-04-01 | P001 | Software Developer | RES04 | 20 | Mobile Banking App | 60 | 0.3333 | Diana Miller | 6800 | 850
2026-04-01 | P001 | Software Developer | RES05 | 20 | Mobile Banking App | 60 | 0.3333 | Ethan Davis | 6400 | 800
2026-04-01 | P001 | Software Developer | RES06 | 20 | Mobile Banking App | 60 | 0.3333 | Fiona Wilson | 6300 | 787.5
2026-04-01 | P011 | Software Developer | RES07 | 20 | ERP Implementation | 60 | 0.3333 | Henry Collins | 6600 | 825
2026-04-01 | P011 | Software Developer | RES08 | 20 | ERP Implementation | 60 | 0.3333 | Isabella Wright | 6700 | 837.5
2026-04-01 | P011 | Software Developer | RES09 | 20 | ERP Implementation | 60 | 0.3333 | Jack Thompson | 6450 | 806.25
2026-04-01 | P011 | Software Developer | RES25 | 20 | ERP Implementation | 60 | 0.3333 | Wendy Brooks | 6550 | 818.75
2026-04-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 80 | 0.25 | Alice Johnson | 6000 | 750
2026-04-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 80 | 0.25 | Bob Smith | 6200 | 775
2026-04-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 60 | 0.3333 | Charlie Brown | 6500 | 812.5
2026-04-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 60 | 0.3333 | Diana Miller | 6800 | 850
2026-04-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 60 | 0.3333 | Ethan Davis | 6400 | 800
2026-04-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 60 | 0.3333 | Fiona Wilson | 6300 | 787.5
2026-04-01 | P011 | Software Developer | RES07 | 20 | ERP Implementation | 60 | 0.3333 | Henry Collins | 6600 | 825
2026-04-01 | P011 | Software Developer | RES08 | 20 | ERP Implementation | 60 | 0.3333 | Isabella Wright | 6700 | 837.5
2026-04-01 | P011 | Software Developer | RES09 | 20 | ERP Implementation | 60 | 0.3333 | Jack Thompson | 6450 | 806.25
2026-04-01 | P011 | Software Developer | RES25 | 20 | ERP Implementation | 60 | 0.3333 | Wendy Brooks | 6550 | 818.75
2026-04-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 80 | 0.25 | Alice Johnson | 6000 | 750
2026-04-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 80 | 0.25 | Bob Smith | 6200 | 775
2026-04-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-04-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-04-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-04-01 | P001 | UX/UI Designer | RES21 | 20 | Mobile Banking App | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-04-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-04-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-04-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-04-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 160 | 0.125 | Rachel Foster | 6200 | 775
2026-05-01 | P011 | Architect | RES23 | 20 | ERP Implementation | 20 | 1 | Tina Murphy | 8000 | 1000
2026-05-01 | P011 | Architect | RES24 | 20 | ERP Implementation | 20 | 1 | Victor Hall | 8200 | 1025
2026-05-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 40 | 0.5 | Samuel Bennett | 6800 | 850
2026-05-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 40 | 0.5 | Samuel Bennett | 6800 | 850
2026-05-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 40 | 0.5 | Natalie Perez | 7500 | 937.5
2026-05-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 40 | 0.5 | Oliver Scott | 7600 | 950
2026-05-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 40 | 0.5 | Paula Edwards | 7400 | 925
2026-05-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 40 | 0.5 | Quentin Hughes | 7700 | 962.5
2026-05-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 40 | 0.5 | Natalie Perez | 7500 | 937.5
2026-05-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 40 | 0.5 | Oliver Scott | 7600 | 950
2026-05-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 40 | 0.5 | Paula Edwards | 7400 | 925
2026-05-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 40 | 0.5 | Quentin Hughes | 7700 | 962.5
2026-05-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 60 | 0.3333 | George Clark | 5000 | 625
2026-05-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 60 | 0.3333 | Hannah Lopez | 5200 | 650
2026-05-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 40 | 0.5 | Ian Martinez | 5100 | 637.5
2026-05-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 60 | 0.3333 | George Clark | 5000 | 625
2026-05-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 60 | 0.3333 | Hannah Lopez | 5200 | 650
2026-05-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 40 | 0.5 | Ian Martinez | 5100 | 637.5
2026-05-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 60 | 0.3333 | George Clark | 5000 | 625
2026-05-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 60 | 0.3333 | Hannah Lopez | 5200 | 650
2026-05-01 | P011 | Scrum Master | RES13 | 20 | ERP Implementation | 20 | 1 | Julia Carter | 7000 | 875
2026-05-01 | P011 | Scrum Master | RES14 | 20 | ERP Implementation | 20 | 1 | Kevin Turner | 7200 | 900
2026-05-01 | P011 | Scrum Master | RES15 | 20 | ERP Implementation | 20 | 1 | Laura Adams | 7100 | 887.5
2026-05-01 | P011 | Scrum Master | RES16 | 20 | ERP Implementation | 20 | 1 | Mark Robinson | 7300 | 912.5
2026-05-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 40 | 0.5 | Alice Johnson | 6000 | 750
2026-05-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 40 | 0.5 | Bob Smith | 6200 | 775
2026-05-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 40 | 0.5 | Charlie Brown | 6500 | 812.5
2026-05-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 40 | 0.5 | Diana Miller | 6800 | 850
2026-05-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 40 | 0.5 | Ethan Davis | 6400 | 800
2026-05-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 40 | 0.5 | Fiona Wilson | 6300 | 787.5
2026-05-01 | P011 | Software Developer | RES07 | 20 | ERP Implementation | 20 | 1 | Henry Collins | 6600 | 825
2026-05-01 | P011 | Software Developer | RES08 | 20 | ERP Implementation | 20 | 1 | Isabella Wright | 6700 | 837.5
2026-05-01 | P011 | Software Developer | RES09 | 20 | ERP Implementation | 20 | 1 | Jack Thompson | 6450 | 806.25
2026-05-01 | P011 | Software Developer | RES25 | 20 | ERP Implementation | 20 | 1 | Wendy Brooks | 6550 | 818.75
2026-05-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 40 | 0.5 | Alice Johnson | 6000 | 750
2026-05-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 40 | 0.5 | Bob Smith | 6200 | 775
2026-05-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 40 | 0.5 | Charlie Brown | 6500 | 812.5
2026-05-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 40 | 0.5 | Diana Miller | 6800 | 850
2026-05-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 40 | 0.5 | Ethan Davis | 6400 | 800
2026-05-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 40 | 0.5 | Fiona Wilson | 6300 | 787.5
2026-05-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-05-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-05-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-05-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-06-01 | P011 | Architect | RES23 | 20 | ERP Implementation | 20 | 1 | Tina Murphy | 8000 | 1000
2026-06-01 | P011 | Architect | RES24 | 20 | ERP Implementation | 20 | 1 | Victor Hall | 8200 | 1025
2026-06-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 40 | 0.5 | Samuel Bennett | 6800 | 850
2026-06-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 40 | 0.5 | Samuel Bennett | 6800 | 850
2026-06-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 40 | 0.5 | Natalie Perez | 7500 | 937.5
2026-06-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 40 | 0.5 | Oliver Scott | 7600 | 950
2026-06-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 40 | 0.5 | Paula Edwards | 7400 | 925
2026-06-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 40 | 0.5 | Quentin Hughes | 7700 | 962.5
2026-06-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 40 | 0.5 | Natalie Perez | 7500 | 937.5
2026-06-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 40 | 0.5 | Oliver Scott | 7600 | 950
2026-06-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 40 | 0.5 | Paula Edwards | 7400 | 925
2026-06-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 40 | 0.5 | Quentin Hughes | 7700 | 962.5
2026-06-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 60 | 0.3333 | George Clark | 5000 | 625
2026-06-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 60 | 0.3333 | Hannah Lopez | 5200 | 650
2026-06-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 40 | 0.5 | Ian Martinez | 5100 | 637.5
2026-06-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 60 | 0.3333 | George Clark | 5000 | 625
2026-06-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 60 | 0.3333 | Hannah Lopez | 5200 | 650
2026-06-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 40 | 0.5 | Ian Martinez | 5100 | 637.5
2026-06-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 60 | 0.3333 | George Clark | 5000 | 625
2026-06-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 60 | 0.3333 | Hannah Lopez | 5200 | 650
2026-06-01 | P011 | Scrum Master | RES13 | 20 | ERP Implementation | 20 | 1 | Julia Carter | 7000 | 875
2026-06-01 | P011 | Scrum Master | RES14 | 20 | ERP Implementation | 20 | 1 | Kevin Turner | 7200 | 900
2026-06-01 | P011 | Scrum Master | RES15 | 20 | ERP Implementation | 20 | 1 | Laura Adams | 7100 | 887.5
2026-06-01 | P011 | Scrum Master | RES16 | 20 | ERP Implementation | 20 | 1 | Mark Robinson | 7300 | 912.5
2026-06-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 40 | 0.5 | Alice Johnson | 6000 | 750
2026-06-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 40 | 0.5 | Bob Smith | 6200 | 775
2026-06-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 40 | 0.5 | Charlie Brown | 6500 | 812.5
2026-06-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 40 | 0.5 | Diana Miller | 6800 | 850
2026-06-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 40 | 0.5 | Ethan Davis | 6400 | 800
2026-06-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 40 | 0.5 | Fiona Wilson | 6300 | 787.5
2026-06-01 | P011 | Software Developer | RES07 | 20 | ERP Implementation | 20 | 1 | Henry Collins | 6600 | 825
2026-06-01 | P011 | Software Developer | RES08 | 20 | ERP Implementation | 20 | 1 | Isabella Wright | 6700 | 837.5
2026-06-01 | P011 | Software Developer | RES09 | 20 | ERP Implementation | 20 | 1 | Jack Thompson | 6450 | 806.25
2026-06-01 | P011 | Software Developer | RES25 | 20 | ERP Implementation | 20 | 1 | Wendy Brooks | 6550 | 818.75
2026-06-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 40 | 0.5 | Alice Johnson | 6000 | 750
2026-06-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 40 | 0.5 | Bob Smith | 6200 | 775
2026-06-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 40 | 0.5 | Charlie Brown | 6500 | 812.5
2026-06-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 40 | 0.5 | Diana Miller | 6800 | 850
2026-06-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 40 | 0.5 | Ethan Davis | 6400 | 800
2026-06-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 40 | 0.5 | Fiona Wilson | 6300 | 787.5
2026-06-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-06-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-06-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-06-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-07-01 | P011 | Architect | RES23 | 20 | ERP Implementation | 20 | 1 | Tina Murphy | 8000 | 1000
2026-07-01 | P011 | Architect | RES24 | 20 | ERP Implementation | 20 | 1 | Victor Hall | 8200 | 1025
2026-07-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 40 | 0.5 | Samuel Bennett | 6800 | 850
2026-07-01 | P011 | DevOps Engineer | RES22 | 20 | ERP Implementation | 40 | 0.5 | Samuel Bennett | 6800 | 850
2026-07-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 40 | 0.5 | Natalie Perez | 7500 | 937.5
2026-07-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 40 | 0.5 | Oliver Scott | 7600 | 950
2026-07-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 40 | 0.5 | Paula Edwards | 7400 | 925
2026-07-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 40 | 0.5 | Quentin Hughes | 7700 | 962.5
2026-07-01 | P011 | Product Owner | RES17 | 20 | ERP Implementation | 40 | 0.5 | Natalie Perez | 7500 | 937.5
2026-07-01 | P011 | Product Owner | RES18 | 20 | ERP Implementation | 40 | 0.5 | Oliver Scott | 7600 | 950
2026-07-01 | P011 | Product Owner | RES19 | 20 | ERP Implementation | 40 | 0.5 | Paula Edwards | 7400 | 925
2026-07-01 | P011 | Product Owner | RES20 | 20 | ERP Implementation | 40 | 0.5 | Quentin Hughes | 7700 | 962.5
2026-07-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 60 | 0.3333 | George Clark | 5000 | 625
2026-07-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 60 | 0.3333 | Hannah Lopez | 5200 | 650
2026-07-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 40 | 0.5 | Ian Martinez | 5100 | 637.5
2026-07-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 60 | 0.3333 | George Clark | 5000 | 625
2026-07-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 60 | 0.3333 | Hannah Lopez | 5200 | 650
2026-07-01 | P011 | QA / Tester | RES12 | 20 | ERP Implementation | 40 | 0.5 | Ian Martinez | 5100 | 637.5
2026-07-01 | P011 | QA / Tester | RES10 | 20 | ERP Implementation | 60 | 0.3333 | George Clark | 5000 | 625
2026-07-01 | P011 | QA / Tester | RES11 | 20 | ERP Implementation | 60 | 0.3333 | Hannah Lopez | 5200 | 650
2026-07-01 | P011 | Scrum Master | RES13 | 20 | ERP Implementation | 20 | 1 | Julia Carter | 7000 | 875
2026-07-01 | P011 | Scrum Master | RES14 | 20 | ERP Implementation | 20 | 1 | Kevin Turner | 7200 | 900
2026-07-01 | P011 | Scrum Master | RES15 | 20 | ERP Implementation | 20 | 1 | Laura Adams | 7100 | 887.5
2026-07-01 | P011 | Scrum Master | RES16 | 20 | ERP Implementation | 20 | 1 | Mark Robinson | 7300 | 912.5
2026-07-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 40 | 0.5 | Alice Johnson | 6000 | 750
2026-07-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 40 | 0.5 | Bob Smith | 6200 | 775
2026-07-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 40 | 0.5 | Charlie Brown | 6500 | 812.5
2026-07-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 40 | 0.5 | Diana Miller | 6800 | 850
2026-07-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 40 | 0.5 | Ethan Davis | 6400 | 800
2026-07-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 40 | 0.5 | Fiona Wilson | 6300 | 787.5
2026-07-01 | P011 | Software Developer | RES07 | 20 | ERP Implementation | 20 | 1 | Henry Collins | 6600 | 825
2026-07-01 | P011 | Software Developer | RES08 | 20 | ERP Implementation | 20 | 1 | Isabella Wright | 6700 | 837.5
2026-07-01 | P011 | Software Developer | RES09 | 20 | ERP Implementation | 20 | 1 | Jack Thompson | 6450 | 806.25
2026-07-01 | P011 | Software Developer | RES25 | 20 | ERP Implementation | 20 | 1 | Wendy Brooks | 6550 | 818.75
2026-07-01 | P011 | Software Developer | RES01 | 20 | ERP Implementation | 40 | 0.5 | Alice Johnson | 6000 | 750
2026-07-01 | P011 | Software Developer | RES02 | 20 | ERP Implementation | 40 | 0.5 | Bob Smith | 6200 | 775
2026-07-01 | P011 | Software Developer | RES03 | 20 | ERP Implementation | 40 | 0.5 | Charlie Brown | 6500 | 812.5
2026-07-01 | P011 | Software Developer | RES04 | 20 | ERP Implementation | 40 | 0.5 | Diana Miller | 6800 | 850
2026-07-01 | P011 | Software Developer | RES05 | 20 | ERP Implementation | 40 | 0.5 | Ethan Davis | 6400 | 800
2026-07-01 | P011 | Software Developer | RES06 | 20 | ERP Implementation | 40 | 0.5 | Fiona Wilson | 6300 | 787.5
2026-07-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-07-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-07-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775
2026-07-01 | P011 | UX/UI Designer | RES21 | 20 | ERP Implementation | 80 | 0.25 | Rachel Foster | 6200 | 775