## Projects_Planned
ProjectID | ProjectName | Status | DurationDays | Start_Date | End_Date
P014 | AI-driven CRM | Planned | 243 | 2025-09-01 | 2026-05-02
P018 | Legacy System Migration | Planned | 382 | 2025-12-25 | 2027-01-11
P012 | Analytics Dashboard | Planned | 369 | 2025-12-28 | 2027-01-01
P015 | DevOps Automation | Planned | 269 | 2025-12-29 | 2026-09-24
P009 | HR System Upgrade | Planned | 314 | 2026-01-19 | 2026-11-29
P017 | Customer Portal | In Sales process | 201 | 2026-01-19 | 2026-08-08
P004 | AI Chatbot | In Sales process | 193 | 2026-02-11 | 2026-08-23
P019 | ML Recommendation Engine | Planned | 230 | 2026-05-03 | 2026-12-19
P010 | Mobile App Revamp | Planned | 217 | 2026-05-06 | 2026-12-09
P007 | Cloud Migration | Planned | 228 | 2026-05-07 | 2026-12-21
P020 | Data Governance Framework | Planned | 271 | 2026-05-09 | 2027-02-04
P008 | IoT Pilot | In Sales process | 187 | 2026-08-26 | 2027-03-01
P013 | Blockchain PoC | Planned | 200 | 2026-09-25 | 2027-04-13

## RoleMonthlyPlanned
ProjectID | ProjectName | Status | Month | Role | HoursPlanned | FTEsPlanned
P014 | AI-driven CRM | Planned | 2025-09-01 | Software Developer | 320 | 2
P014 | AI-driven CRM | Planned | 2025-09-01 | QA / Tester | 160 | 1
P014 | AI-driven CRM | Planned | 2025-09-01 | Scrum Master | 80 | 0.5
P014 | AI-driven CRM | Planned | 2025-09-01 | Product Owner | 160 | 1
P014 | AI-driven CRM | Planned | 2025-09-01 | UX/UI Designer | 80 | 0.5
P014 | AI-driven CRM | Planned | 2025-09-01 | DevOps Engineer | 40 | 0.25
P014 | AI-driven CRM | Planned | 2025-09-01 | Architect | 40 | 0.25
P014 | AI-driven CRM | Planned | 2025-10-01 | Software Developer | 320 | 2
P014 | AI-driven CRM | Planned | 2025-10-01 | QA / Tester | 160 | 1
P014 | AI-driven CRM | Planned | 2025-10-01 | Scrum Master | 80 | 0.5
P014 | AI-driven CRM | Planned | 2025-10-01 | Product Owner | 160 | 1
P014 | AI-driven CRM | Planned | 2025-10-01 | UX/UI Designer | 80 | 0.5
P014 | AI-driven CRM | Planned | 2025-10-01 | DevOps Engineer | 40 | 0.25
P014 | AI-driven CRM | Planned | 2025-10-01 | Architect | 40 | 0.25
P014 | AI-driven CRM | Planned | 2025-11-01 | Software Developer | 320 | 2
P014 | AI-driven CRM | Planned | 2025-11-01 | QA / Tester | 160 | 1
P014 | AI-driven CRM | Planned | 2025-11-01 | Scrum Master | 80 | 0.5
P014 | AI-driven CRM | Planned | 2025-11-01 | Product Owner | 160 | 1
P014 | AI-driven CRM | Planned | 2025-11-01 | UX/UI Designer | 80 | 0.5
P014 | AI-driven CRM | Planned | 2025-11-01 | DevOps Engineer | 40 | 0.25
P014 | AI-driven CRM | Planned | 2025-11-01 | Architect | 40 | 0.25
P014 | AI-driven CRM | Planned | 2025-12-01 | Software Developer | 320 | 2
P014 | AI-driven CRM | Planned | 2025-12-01 | QA / Tester | 160 | 1
P014 | AI-driven CRM | Planned | 2025-12-01 | Scrum Master | 80 | 0.5
P014 | AI-driven CRM | Planned | 2025-12-01 | Product Owner | 160 | 1
P014 | AI-driven CRM | Planned | 2025-12-01 | UX/UI Designer | 80 | 0.5
P014 | AI-driven CRM | Planned | 2025-12-01 | DevOps Engineer | 40 | 0.25
P014 | AI-driven CRM | Planned | 2025-12-01 | Architect | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-01-01 | Software Developer | 320 | 2
P014 | AI-driven CRM | Planned | 2026-01-01 | QA / Tester | 160 | 1
P014 | AI-driven CRM | Planned | 2026-01-01 | Scrum Master | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-01-01 | Product Owner | 160 | 1
P014 | AI-driven CRM | Planned | 2026-01-01 | UX/UI Designer | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-01-01 | DevOps Engineer | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-01-01 | Architect | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-02-01 | Software Developer | 320 | 2
P014 | AI-driven CRM | Planned | 2026-02-01 | QA / Tester | 160 | 1
P014 | AI-driven CRM | Planned | 2026-02-01 | Scrum Master | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-02-01 | Product Owner | 160 | 1
P014 | AI-driven CRM | Planned | 2026-02-01 | UX/UI Designer | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-02-01 | DevOps Engineer | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-02-01 | Architect | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-03-01 | Software Developer | 320 | 2
P014 | AI-driven CRM | Planned | 2026-03-01 | QA / Tester | 160 | 1
P014 | AI-driven CRM | Planned | 2026-03-01 | Scrum Master | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-03-01 | Product Owner | 160 | 1
P014 | AI-driven CRM | Planned | 2026-03-01 | UX/UI Designer | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-03-01 | DevOps Engineer | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-03-01 | Architect | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-04-01 | Software Developer | 320 | 2
P014 | AI-driven CRM | Planned | 2026-04-01 | QA / Tester | 160 | 1
P014 | AI-driven CRM | Planned | 2026-04-01 | Scrum Master | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-04-01 | Product Owner | 160 | 1
P014 | AI-driven CRM | Planned | 2026-04-01 | UX/UI Designer | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-04-01 | DevOps Engineer | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-04-01 | Architect | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-05-01 | Software Developer | 320 | 2
P014 | AI-driven CRM | Planned | 2026-05-01 | QA / Tester | 160 | 1
P014 | AI-driven CRM | Planned | 2026-05-01 | Scrum Master | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-05-01 | Product Owner | 160 | 1
P014 | AI-driven CRM | Planned | 2026-05-01 | UX/UI Designer | 80 | 0.5
P014 | AI-driven CRM | Planned | 2026-05-01 | DevOps Engineer | 40 | 0.25
P014 | AI-driven CRM | Planned | 2026-05-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2025-12-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2025-12-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2025-12-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2025-12-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2025-12-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2025-12-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2025-12-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-01-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-01-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-01-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-01-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-01-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-01-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-01-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-02-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-02-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-02-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-02-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-02-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-02-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-02-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-03-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-03-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-03-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-03-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-03-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-03-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-03-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-04-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-04-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-04-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-04-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-04-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-04-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-04-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-05-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-05-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-05-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-05-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-05-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-05-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-05-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-06-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-06-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-06-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-06-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-06-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-06-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-06-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-07-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-07-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-07-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-07-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-07-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-07-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-07-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-08-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-08-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-08-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-08-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-08-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-08-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-08-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-09-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-09-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-09-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-09-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-09-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-09-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-09-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-10-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-10-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-10-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-10-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-10-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-10-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-10-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-11-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-11-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-11-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-11-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-11-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-11-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-11-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-12-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2026-12-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2026-12-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-12-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2026-12-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2026-12-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2026-12-01 | Architect | 40 | 0.25
P018 | Legacy System Migration | Planned | 2027-01-01 | Software Developer | 320 | 2
P018 | Legacy System Migration | Planned | 2027-01-01 | QA / Tester | 160 | 1
P018 | Legacy System Migration | Planned | 2027-01-01 | Scrum Master | 80 | 0.5
P018 | Legacy System Migration | Planned | 2027-01-01 | Product Owner | 160 | 1
P018 | Legacy System Migration | Planned | 2027-01-01 | UX/UI Designer | 80 | 0.5
P018 | Legacy System Migration | Planned | 2027-01-01 | DevOps Engineer | 40 | 0.25
P018 | Legacy System Migration | Planned | 2027-01-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2025-12-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2025-12-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2025-12-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2025-12-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2025-12-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2025-12-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2025-12-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-01-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-01-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-01-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-01-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-01-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-01-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-01-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-02-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-02-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-02-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-02-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-02-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-02-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-02-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-03-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-03-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-03-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-03-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-03-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-03-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-03-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-04-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-04-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-04-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-04-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-04-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-04-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-04-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-05-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-05-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-05-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-05-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-05-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-05-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-05-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-06-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-06-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-06-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-06-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-06-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-06-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-06-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-07-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-07-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-07-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-07-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-07-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-07-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-07-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-08-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-08-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-08-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-08-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-08-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-08-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-08-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-09-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-09-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-09-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-09-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-09-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-09-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-09-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-10-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-10-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-10-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-10-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-10-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-10-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-10-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-11-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-11-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-11-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-11-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-11-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-11-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-11-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-12-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2026-12-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-12-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-12-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2026-12-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2026-12-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2026-12-01 | Architect | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2027-01-01 | Software Developer | 320 | 2
P012 | Analytics Dashboard | Planned | 2027-01-01 | QA / Tester | 160 | 1
P012 | Analytics Dashboard | Planned | 2027-01-01 | Scrum Master | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2027-01-01 | Product Owner | 160 | 1
P012 | Analytics Dashboard | Planned | 2027-01-01 | UX/UI Designer | 80 | 0.5
P012 | Analytics Dashboard | Planned | 2027-01-01 | DevOps Engineer | 40 | 0.25
P012 | Analytics Dashboard | Planned | 2027-01-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2025-12-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2025-12-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2025-12-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2025-12-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2025-12-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2025-12-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2025-12-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-01-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2026-01-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2026-01-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-01-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2026-01-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-01-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-01-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-02-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2026-02-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2026-02-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-02-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2026-02-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-02-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-02-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-03-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2026-03-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2026-03-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-03-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2026-03-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-03-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-03-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-04-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2026-04-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2026-04-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-04-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2026-04-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-04-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-04-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-05-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2026-05-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2026-05-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-05-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2026-05-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-05-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-05-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-06-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2026-06-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2026-06-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-06-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2026-06-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-06-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-06-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-07-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2026-07-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2026-07-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-07-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2026-07-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-07-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-07-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-08-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2026-08-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2026-08-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-08-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2026-08-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-08-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-08-01 | Architect | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-09-01 | Software Developer | 320 | 2
P015 | DevOps Automation | Planned | 2026-09-01 | QA / Tester | 160 | 1
P015 | DevOps Automation | Planned | 2026-09-01 | Scrum Master | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-09-01 | Product Owner | 160 | 1
P015 | DevOps Automation | Planned | 2026-09-01 | UX/UI Designer | 80 | 0.5
P015 | DevOps Automation | Planned | 2026-09-01 | DevOps Engineer | 40 | 0.25
P015 | DevOps Automation | Planned | 2026-09-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-01-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-01-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-01-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-01-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-01-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-01-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-01-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-02-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-02-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-02-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-02-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-02-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-02-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-02-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-03-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-03-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-03-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-03-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-03-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-03-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-03-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-04-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-04-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-04-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-04-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-04-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-04-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-04-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-05-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-05-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-05-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-05-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-05-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-05-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-05-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-06-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-06-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-06-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-06-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-06-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-06-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-06-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-07-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-07-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-07-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-07-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-07-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-07-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-07-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-08-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-08-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-08-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-08-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-08-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-08-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-08-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-09-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-09-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-09-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-09-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-09-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-09-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-09-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-10-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-10-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-10-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-10-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-10-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-10-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-10-01 | Architect | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-11-01 | Software Developer | 320 | 2
P009 | HR System Upgrade | Planned | 2026-11-01 | QA / Tester | 160 | 1
P009 | HR System Upgrade | Planned | 2026-11-01 | Scrum Master | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-11-01 | Product Owner | 160 | 1
P009 | HR System Upgrade | Planned | 2026-11-01 | UX/UI Designer | 80 | 0.5
P009 | HR System Upgrade | Planned | 2026-11-01 | DevOps Engineer | 40 | 0.25
P009 | HR System Upgrade | Planned | 2026-11-01 | Architect | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-01-01 | Software Developer | 320 | 2
P017 | Customer Portal | In Sales process | 2026-01-01 | QA / Tester | 160 | 1
P017 | Customer Portal | In Sales process | 2026-01-01 | Scrum Master | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-01-01 | Product Owner | 160 | 1
P017 | Customer Portal | In Sales process | 2026-01-01 | UX/UI Designer | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-01-01 | DevOps Engineer | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-01-01 | Architect | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-02-01 | Software Developer | 320 | 2
P017 | Customer Portal | In Sales process | 2026-02-01 | QA / Tester | 160 | 1
P017 | Customer Portal | In Sales process | 2026-02-01 | Scrum Master | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-02-01 | Product Owner | 160 | 1
P017 | Customer Portal | In Sales process | 2026-02-01 | UX/UI Designer | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-02-01 | DevOps Engineer | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-02-01 | Architect | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-03-01 | Software Developer | 320 | 2
P017 | Customer Portal | In Sales process | 2026-03-01 | QA / Tester | 160 | 1
P017 | Customer Portal | In Sales process | 2026-03-01 | Scrum Master | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-03-01 | Product Owner | 160 | 1
P017 | Customer Portal | In Sales process | 2026-03-01 | UX/UI Designer | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-03-01 | DevOps Engineer | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-03-01 | Architect | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-04-01 | Software Developer | 320 | 2
P017 | Customer Portal | In Sales process | 2026-04-01 | QA / Tester | 160 | 1
P017 | Customer Portal | In Sales process | 2026-04-01 | Scrum Master | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-04-01 | Product Owner | 160 | 1
P017 | Customer Portal | In Sales process | 2026-04-01 | UX/UI Designer | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-04-01 | DevOps Engineer | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-04-01 | Architect | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-05-01 | Software Developer | 320 | 2
P017 | Customer Portal | In Sales process | 2026-05-01 | QA / Tester | 160 | 1
P017 | Customer Portal | In Sales process | 2026-05-01 | Scrum Master | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-05-01 | Product Owner | 160 | 1
P017 | Customer Portal | In Sales process | 2026-05-01 | UX/UI Designer | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-05-01 | DevOps Engineer | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-05-01 | Architect | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-06-01 | Software Developer | 320 | 2
P017 | Customer Portal | In Sales process | 2026-06-01 | QA / Tester | 160 | 1
P017 | Customer Portal | In Sales process | 2026-06-01 | Scrum Master | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-06-01 | Product Owner | 160 | 1
P017 | Customer Portal | In Sales process | 2026-06-01 | UX/UI Designer | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-06-01 | DevOps Engineer | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-06-01 | Architect | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-07-01 | Software Developer | 320 | 2
P017 | Customer Portal | In Sales process | 2026-07-01 | QA / Tester | 160 | 1
P017 | Customer Portal | In Sales process | 2026-07-01 | Scrum Master | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-07-01 | Product Owner | 160 | 1
P017 | Customer Portal | In Sales process | 2026-07-01 | UX/UI Designer | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-07-01 | DevOps Engineer | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-07-01 | Architect | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-08-01 | Software Developer | 320 | 2
P017 | Customer Portal | In Sales process | 2026-08-01 | QA / Tester | 160 | 1
P017 | Customer Portal | In Sales process | 2026-08-01 | Scrum Master | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-08-01 | Product Owner | 160 | 1
P017 | Customer Portal | In Sales process | 2026-08-01 | UX/UI Designer | 80 | 0.5
P017 | Customer Portal | In Sales process | 2026-08-01 | DevOps Engineer | 40 | 0.25
P017 | Customer Portal | In Sales process | 2026-08-01 | Architect | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-02-01 | Software Developer | 320 | 2
P004 | AI Chatbot | In Sales process | 2026-02-01 | QA / Tester | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-02-01 | Scrum Master | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-02-01 | Product Owner | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-02-01 | UX/UI Designer | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-02-01 | DevOps Engineer | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-02-01 | Architect | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-03-01 | Software Developer | 320 | 2
P004 | AI Chatbot | In Sales process | 2026-03-01 | QA / Tester | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-03-01 | Scrum Master | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-03-01 | Product Owner | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-03-01 | UX/UI Designer | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-03-01 | DevOps Engineer | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-03-01 | Architect | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-04-01 | Software Developer | 320 | 2
P004 | AI Chatbot | In Sales process | 2026-04-01 | QA / Tester | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-04-01 | Scrum Master | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-04-01 | Product Owner | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-04-01 | UX/UI Designer | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-04-01 | DevOps Engineer | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-04-01 | Architect | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-05-01 | Software Developer | 320 | 2
P004 | AI Chatbot | In Sales process | 2026-05-01 | QA / Tester | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-05-01 | Scrum Master | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-05-01 | Product Owner | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-05-01 | UX/UI Designer | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-05-01 | DevOps Engineer | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-05-01 | Architect | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-06-01 | Software Developer | 320 | 2
P004 | AI Chatbot | In Sales process | 2026-06-01 | QA / Tester | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-06-01 | Scrum Master | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-06-01 | Product Owner | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-06-01 | UX/UI Designer | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-06-01 | DevOps Engineer | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-06-01 | Architect | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-07-01 | Software Developer | 320 | 2
P004 | AI Chatbot | In Sales process | 2026-07-01 | QA / Tester | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-07-01 | Scrum Master | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-07-01 | Product Owner | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-07-01 | UX/UI Designer | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-07-01 | DevOps Engineer | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-07-01 | Architect | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-08-01 | Software Developer | 320 | 2
P004 | AI Chatbot | In Sales process | 2026-08-01 | QA / Tester | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-08-01 | Scrum Master | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-08-01 | Product Owner | 160 | 1
P004 | AI Chatbot | In Sales process | 2026-08-01 | UX/UI Designer | 80 | 0.5
P004 | AI Chatbot | In Sales process | 2026-08-01 | DevOps Engineer | 40 | 0.25
P004 | AI Chatbot | In Sales process | 2026-08-01 | Architect | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-05-01 | Software Developer | 320 | 2
P019 | ML Recommendation Engine | Planned | 2026-05-01 | QA / Tester | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-05-01 | Scrum Master | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-05-01 | Product Owner | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-05-01 | UX/UI Designer | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-05-01 | DevOps Engineer | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-05-01 | Architect | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-06-01 | Software Developer | 320 | 2
P019 | ML Recommendation Engine | Planned | 2026-06-01 | QA / Tester | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-06-01 | Scrum Master | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-06-01 | Product Owner | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-06-01 | UX/UI Designer | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-06-01 | DevOps Engineer | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-06-01 | Architect | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-07-01 | Software Developer | 320 | 2
P019 | ML Recommendation Engine | Planned | 2026-07-01 | QA / Tester | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-07-01 | Scrum Master | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-07-01 | Product Owner | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-07-01 | UX/UI Designer | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-07-01 | DevOps Engineer | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-07-01 | Architect | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-08-01 | Software Developer | 320 | 2
P019 | ML Recommendation Engine | Planned | 2026-08-01 | QA / Tester | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-08-01 | Scrum Master | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-08-01 | Product Owner | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-08-01 | UX/UI Designer | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-08-01 | DevOps Engineer | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-08-01 | Architect | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-09-01 | Software Developer | 320 | 2
P019 | ML Recommendation Engine | Planned | 2026-09-01 | QA / Tester | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-09-01 | Scrum Master | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-09-01 | Product Owner | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-09-01 | UX/UI Designer | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-09-01 | DevOps Engineer | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-09-01 | Architect | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-10-01 | Software Developer | 320 | 2
P019 | ML Recommendation Engine | Planned | 2026-10-01 | QA / Tester | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-10-01 | Scrum Master | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-10-01 | Product Owner | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-10-01 | UX/UI Designer | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-10-01 | DevOps Engineer | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-10-01 | Architect | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-11-01 | Software Developer | 320 | 2
P019 | ML Recommendation Engine | Planned | 2026-11-01 | QA / Tester | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-11-01 | Scrum Master | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-11-01 | Product Owner | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-11-01 | UX/UI Designer | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-11-01 | DevOps Engineer | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-11-01 | Architect | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-12-01 | Software Developer | 320 | 2
P019 | ML Recommendation Engine | Planned | 2026-12-01 | QA / Tester | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-12-01 | Scrum Master | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-12-01 | Product Owner | 160 | 1
P019 | ML Recommendation Engine | Planned | 2026-12-01 | UX/UI Designer | 80 | 0.5
P019 | ML Recommendation Engine | Planned | 2026-12-01 | DevOps Engineer | 40 | 0.25
P019 | ML Recommendation Engine | Planned | 2026-12-01 | Architect | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-05-01 | Software Developer | 320 | 2
P010 | Mobile App Revamp | Planned | 2026-05-01 | QA / Tester | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-05-01 | Scrum Master | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-05-01 | Product Owner | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-05-01 | UX/UI Designer | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-05-01 | DevOps Engineer | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-05-01 | Architect | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-06-01 | Software Developer | 320 | 2
P010 | Mobile App Revamp | Planned | 2026-06-01 | QA / Tester | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-06-01 | Scrum Master | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-06-01 | Product Owner | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-06-01 | UX/UI Designer | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-06-01 | DevOps Engineer | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-06-01 | Architect | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-07-01 | Software Developer | 320 | 2
P010 | Mobile App Revamp | Planned | 2026-07-01 | QA / Tester | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-07-01 | Scrum Master | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-07-01 | Product Owner | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-07-01 | UX/UI Designer | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-07-01 | DevOps Engineer | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-07-01 | Architect | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-08-01 | Software Developer | 320 | 2
P010 | Mobile App Revamp | Planned | 2026-08-01 | QA / Tester | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-08-01 | Scrum Master | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-08-01 | Product Owner | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-08-01 | UX/UI Designer | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-08-01 | DevOps Engineer | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-08-01 | Architect | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-09-01 | Software Developer | 320 | 2
P010 | Mobile App Revamp | Planned | 2026-09-01 | QA / Tester | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-09-01 | Scrum Master | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-09-01 | Product Owner | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-09-01 | UX/UI Designer | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-09-01 | DevOps Engineer | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-09-01 | Architect | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-10-01 | Software Developer | 320 | 2
P010 | Mobile App Revamp | Planned | 2026-10-01 | QA / Tester | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-10-01 | Scrum Master | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-10-01 | Product Owner | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-10-01 | UX/UI Designer | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-10-01 | DevOps Engineer | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-10-01 | Architect | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-11-01 | Software Developer | 320 | 2
P010 | Mobile App Revamp | Planned | 2026-11-01 | QA / Tester | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-11-01 | Scrum Master | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-11-01 | Product Owner | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-11-01 | UX/UI Designer | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-11-01 | DevOps Engineer | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-11-01 | Architect | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-12-01 | Software Developer | 320 | 2
P010 | Mobile App Revamp | Planned | 2026-12-01 | QA / Tester | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-12-01 | Scrum Master | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-12-01 | Product Owner | 160 | 1
P010 | Mobile App Revamp | Planned | 2026-12-01 | UX/UI Designer | 80 | 0.5
P010 | Mobile App Revamp | Planned | 2026-12-01 | DevOps Engineer | 40 | 0.25
P010 | Mobile App Revamp | Planned | 2026-12-01 | Architect | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-05-01 | Software Developer | 320 | 2
P007 | Cloud Migration | Planned | 2026-05-01 | QA / Tester | 160 | 1
P007 | Cloud Migration | Planned | 2026-05-01 | Scrum Master | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-05-01 | Product Owner | 160 | 1
P007 | Cloud Migration | Planned | 2026-05-01 | UX/UI Designer | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-05-01 | DevOps Engineer | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-05-01 | Architect | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-06-01 | Software Developer | 320 | 2
P007 | Cloud Migration | Planned | 2026-06-01 | QA / Tester | 160 | 1
P007 | Cloud Migration | Planned | 2026-06-01 | Scrum Master | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-06-01 | Product Owner | 160 | 1
P007 | Cloud Migration | Planned | 2026-06-01 | UX/UI Designer | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-06-01 | DevOps Engineer | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-06-01 | Architect | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-07-01 | Software Developer | 320 | 2
P007 | Cloud Migration | Planned | 2026-07-01 | QA / Tester | 160 | 1
P007 | Cloud Migration | Planned | 2026-07-01 | Scrum Master | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-07-01 | Product Owner | 160 | 1
P007 | Cloud Migration | Planned | 2026-07-01 | UX/UI Designer | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-07-01 | DevOps Engineer | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-07-01 | Architect | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-08-01 | Software Developer | 320 | 2
P007 | Cloud Migration | Planned | 2026-08-01 | QA / Tester | 160 | 1
P007 | Cloud Migration | Planned | 2026-08-01 | Scrum Master | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-08-01 | Product Owner | 160 | 1
P007 | Cloud Migration | Planned | 2026-08-01 | UX/UI Designer | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-08-01 | DevOps Engineer | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-08-01 | Architect | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-09-01 | Software Developer | 320 | 2
P007 | Cloud Migration | Planned | 2026-09-01 | QA / Tester | 160 | 1
P007 | Cloud Migration | Planned | 2026-09-01 | Scrum Master | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-09-01 | Product Owner | 160 | 1
P007 | Cloud Migration | Planned | 2026-09-01 | UX/UI Designer | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-09-01 | DevOps Engineer | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-09-01 | Architect | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-10-01 | Software Developer | 320 | 2
P007 | Cloud Migration | Planned | 2026-10-01 | QA / Tester | 160 | 1
P007 | Cloud Migration | Planned | 2026-10-01 | Scrum Master | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-10-01 | Product Owner | 160 | 1
P007 | Cloud Migration | Planned | 2026-10-01 | UX/UI Designer | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-10-01 | DevOps Engineer | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-10-01 | Architect | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-11-01 | Software Developer | 320 | 2
P007 | Cloud Migration | Planned | 2026-11-01 | QA / Tester | 160 | 1
P007 | Cloud Migration | Planned | 2026-11-01 | Scrum Master | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-11-01 | Product Owner | 160 | 1
P007 | Cloud Migration | Planned | 2026-11-01 | UX/UI Designer | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-11-01 | DevOps Engineer | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-11-01 | Architect | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-12-01 | Software Developer | 320 | 2
P007 | Cloud Migration | Planned | 2026-12-01 | QA / Tester | 160 | 1
P007 | Cloud Migration | Planned | 2026-12-01 | Scrum Master | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-12-01 | Product Owner | 160 | 1
P007 | Cloud Migration | Planned | 2026-12-01 | UX/UI Designer | 80 | 0.5
P007 | Cloud Migration | Planned | 2026-12-01 | DevOps Engineer | 40 | 0.25
P007 | Cloud Migration | Planned | 2026-12-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-05-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2026-05-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2026-05-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-05-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2026-05-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-05-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-05-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-06-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2026-06-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2026-06-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-06-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2026-06-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-06-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-06-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-07-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2026-07-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2026-07-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-07-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2026-07-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-07-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-07-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-08-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2026-08-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2026-08-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-08-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2026-08-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-08-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-08-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-09-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2026-09-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2026-09-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-09-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2026-09-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-09-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-09-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-10-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2026-10-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2026-10-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-10-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2026-10-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-10-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-10-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-11-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2026-11-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2026-11-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-11-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2026-11-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-11-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-11-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-12-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2026-12-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2026-12-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-12-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2026-12-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2026-12-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2026-12-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2027-01-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2027-01-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2027-01-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2027-01-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2027-01-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2027-01-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2027-01-01 | Architect | 40 | 0.25
P020 | Data Governance Framework | Planned | 2027-02-01 | Software Developer | 320 | 2
P020 | Data Governance Framework | Planned | 2027-02-01 | QA / Tester | 160 | 1
P020 | Data Governance Framework | Planned | 2027-02-01 | Scrum Master | 80 | 0.5
P020 | Data Governance Framework | Planned | 2027-02-01 | Product Owner | 160 | 1
P020 | Data Governance Framework | Planned | 2027-02-01 | UX/UI Designer | 80 | 0.5
P020 | Data Governance Framework | Planned | 2027-02-01 | DevOps Engineer | 40 | 0.25
P020 | Data Governance Framework | Planned | 2027-02-01 | Architect | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-08-01 | Software Developer | 320 | 2
P008 | IoT Pilot | In Sales process | 2026-08-01 | QA / Tester | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-08-01 | Scrum Master | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-08-01 | Product Owner | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-08-01 | UX/UI Designer | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-08-01 | DevOps Engineer | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-08-01 | Architect | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-09-01 | Software Developer | 320 | 2
P008 | IoT Pilot | In Sales process | 2026-09-01 | QA / Tester | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-09-01 | Scrum Master | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-09-01 | Product Owner | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-09-01 | UX/UI Designer | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-09-01 | DevOps Engineer | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-09-01 | Architect | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-10-01 | Software Developer | 320 | 2
P008 | IoT Pilot | In Sales process | 2026-10-01 | QA / Tester | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-10-01 | Scrum Master | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-10-01 | Product Owner | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-10-01 | UX/UI Designer | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-10-01 | DevOps Engineer | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-10-01 | Architect | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-11-01 | Software Developer | 320 | 2
P008 | IoT Pilot | In Sales process | 2026-11-01 | QA / Tester | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-11-01 | Scrum Master | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-11-01 | Product Owner | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-11-01 | UX/UI Designer | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-11-01 | DevOps Engineer | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-11-01 | Architect | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-12-01 | Software Developer | 320 | 2
P008 | IoT Pilot | In Sales process | 2026-12-01 | QA / Tester | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-12-01 | Scrum Master | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-12-01 | Product Owner | 160 | 1
P008 | IoT Pilot | In Sales process | 2026-12-01 | UX/UI Designer | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2026-12-01 | DevOps Engineer | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2026-12-01 | Architect | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2027-01-01 | Software Developer | 320 | 2
P008 | IoT Pilot | In Sales process | 2027-01-01 | QA / Tester | 160 | 1
P008 | IoT Pilot | In Sales process | 2027-01-01 | Scrum Master | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2027-01-01 | Product Owner | 160 | 1
P008 | IoT Pilot | In Sales process | 2027-01-01 | UX/UI Designer | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2027-01-01 | DevOps Engineer | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2027-01-01 | Architect | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2027-02-01 | Software Developer | 320 | 2
P008 | IoT Pilot | In Sales process | 2027-02-01 | QA / Tester | 160 | 1
P008 | IoT Pilot | In Sales process | 2027-02-01 | Scrum Master | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2027-02-01 | Product Owner | 160 | 1
P008 | IoT Pilot | In Sales process | 2027-02-01 | UX/UI Designer | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2027-02-01 | DevOps Engineer | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2027-02-01 | Architect | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2027-03-01 | Software Developer | 320 | 2
P008 | IoT Pilot | In Sales process | 2027-03-01 | QA / Tester | 160 | 1
P008 | IoT Pilot | In Sales process | 2027-03-01 | Scrum Master | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2027-03-01 | Product Owner | 160 | 1
P008 | IoT Pilot | In Sales process | 2027-03-01 | UX/UI Designer | 80 | 0.5
P008 | IoT Pilot | In Sales process | 2027-03-01 | DevOps Engineer | 40 | 0.25
P008 | IoT Pilot | In Sales process | 2027-03-01 | Architect | 40 | 0.25
P013 | Blockchain PoC | Planned | 2026-09-01 | Software Developer | 320 | 2
P013 | Blockchain PoC | Planned | 2026-09-01 | QA / Tester | 160 | 1
P013 | Blockchain PoC | Planned | 2026-09-01 | Scrum Master | 80 | 0.5
P013 | Blockchain PoC | Planned | 2026-09-01 | Product Owner | 160 | 1
P013 | Blockchain PoC | Planned | 2026-09-01 | UX/UI Designer | 80 | 0.5
P013 | Blockchain PoC | Planned | 2026-09-01 | DevOps Engineer | 40 | 0.25
P013 | Blockchain PoC | Planned | 2026-09-01 | Architect | 40 | 0.25
P013 | Blockchain PoC | Planned | 2026-10-01 | Software Developer | 320 | 2
P013 | Blockchain PoC | Planned | 2026-10-01 | QA / Tester | 160 | 1
P013 | Blockchain PoC | Planned | 2026-10-01 | Scrum Master | 80 | 0.5
P013 | Blockchain PoC | Planned | 2026-10-01 | Product Owner | 160 | 1
P013 | Blockchain PoC | Planned | 2026-10-01 | UX/UI Designer | 80 | 0.5
P013 | Blockchain PoC | Planned | 2026-10-01 | DevOps Engineer | 40 | 0.25
P013 | Blockchain PoC | Planned | 2026-10-01 | Architect | 40 | 0.25
P013 | Blockchain PoC | Planned | 2026-11-01 | Software Developer | 320 | 2
P013 | Blockchain PoC | Planned | 2026-11-01 | QA / Tester | 160 | 1
P013 | Blockchain PoC | Planned | 2026-11-01 | Scrum Master | 80 | 0.5
P013 | Blockchain PoC | Planned | 2026-11-01 | Product Owner | 160 | 1
P013 | Blockchain PoC | Planned | 2026-11-01 | UX/UI Designer | 80 | 0.5
P013 | Blockchain PoC | Planned | 2026-11-01 | DevOps Engineer | 40 | 0.25
P013 | Blockchain PoC | Planned | 2026-11-01 | Architect | 40 | 0.25
P013 | Blockchain PoC | Planned | 2026-12-01 | Software Developer | 320 | 2
P013 | Blockchain PoC | Planned | 2026-12-01 | QA / Tester | 160 | 1
P013 | Blockchain PoC | Planned | 2026-12-01 | Scrum Master | 80 | 0.5
P013 | Blockchain PoC | Planned | 2026-12-01 | Product Owner | 160 | 1
P013 | Blockchain PoC | Planned | 2026-12-01 | UX/UI Designer | 80 | 0.5
P013 | Blockchain PoC | Planned | 2026-12-01 | DevOps Engineer | 40 | 0.25
P013 | Blockchain PoC | Planned | 2026-12-01 | Architect | 40 | 0.25
P013 | Blockchain PoC | Planned | 2027-01-01 | Software Developer | 320 | 2
P013 | Blockchain PoC | Planned | 2027-01-01 | QA / Tester | 160 | 1
P013 | Blockchain PoC | Planned | 2027-01-01 | Scrum Master | 80 | 0.5
P013 | Blockchain PoC | Planned | 2027-01-01 | Product Owner | 160 | 1
P013 | Blockchain PoC | Planned | 2027-01-01 | UX/UI Designer | 80 | 0.5
P013 | Blockchain PoC | Planned | 2027-01-01 | DevOps Engineer | 40 | 0.25
P013 | Blockchain PoC | Planned | 2027-01-01 | Architect | 40 | 0.25
P013 | Blockchain PoC | Planned | 2027-02-01 | Software Developer | 320 | 2
P013 | Blockchain PoC | Planned | 2027-02-01 | QA / Tester | 160 | 1
P013 | Blockchain PoC | Planned | 2027-02-01 | Scrum Master | 80 | 0.5
P013 | Blockchain PoC | Planned | 2027-02-01 | Product Owner | 160 | 1
P013 | Blockchain PoC | Planned | 2027-02-01 | UX/UI Designer | 80 | 0.5
P013 | Blockchain PoC | Planned | 2027-02-01 | DevOps Engineer | 40 | 0.25
P013 | Blockchain PoC | Planned | 2027-02-01 | Architect | 40 | 0.25
P013 | Blockchain PoC | Planned | 2027-03-01 | Software Developer | 320 | 2
P013 | Blockchain PoC | Planned | 2027-03-01 | QA / Tester | 160 | 1
P013 | Blockchain PoC | Planned | 2027-03-01 | Scrum Master | 80 | 0.5
P013 | Blockchain PoC | Planned | 2027-03-01 | Product Owner | 160 | 1
P013 | Blockchain PoC | Planned | 2027-03-01 | UX/UI Designer | 80 | 0.5
P013 | Blockchain PoC | Planned | 2027-03-01 | DevOps Engineer | 40 | 0.25
P013 | Blockchain PoC | Planned | 2027-03-01 | Architect | 40 | 0.25
P013 | Blockchain PoC | Planned | 2027-04-01 | Software Developer | 320 | 2
P013 | Blockchain PoC | Planned | 2027-04-01 | QA / Tester | 160 | 1
P013 | Blockchain PoC | Planned | 2027-04-01 | Scrum Master | 80 | 0.5
P013 | Blockchain PoC | Planned | 2027-04-01 | Product Owner | 160 | 1
P013 | Blockchain PoC | Planned | 2027-04-01 | UX/UI Designer | 80 | 0.5
P013 | Blockchain PoC | Planned | 2027-04-01 | DevOps Engineer | 40 | 0.25
P013 | Blockchain PoC | Planned | 2027-04-01 | Architect | 40 | 0.25